## Jira Import
Task ID | Issue Type | Jira Task | Description / Definition of Done | Sprint / Day | Portal / Layer | Epic | Module | Priority | Story Points | Est. Hours | Dependencies | Dependency Category | SRS Traceability | Flow
VKT-001 | Task | Baseline implementation traceability | Create the implementation traceability matrix from every SRS module, requirement ID, state machine, event and release gate to Jira epics/tasks. Treat SRS business rules and state machines as authoritative. | Sprint 1 | Platform | Foundation | Architecture | Must | 2 | 3 | None | BLOCKING | SRS §Document Governance; §31 | SRS -> Jira Epic/Task -> API -> UI -> QA acceptance criterion.
VKT-002 | Task | Define tenant ownership model | Define platform/agency/customer/agent/financial ownership relationships and enforce the rule that customer-owned objects retain both customer and agency ownership where required. | Sprint 1 | Platform | Foundation | Domain model | Must | 5 | 6 | None | BLOCKING | TEN-001..006; §23 | Platform -> Agency -> Customer -> Agent; Financial transaction links platform/agency/customer.
VKT-003 | Task | Create core identity and tenancy tables | Implement Agency, Customer, User and Role persistence with status fields and scope boundaries. Do not allow financial/KYC/audit records to be hard-deleted through normal flows. | Sprint 1 | Platform | Foundation | Database | Must | 5 | 7 | VKT-002 | BLOCKING | §23; TEN-001..006; RBAC-001..006 | Create tenant -> assign owner -> assign scoped role -> persist status/ownership.
VKT-004 | Task | Create commercial and financial tables | Implement Plan/version, Subscription, Invoice, Payment, CommissionEntry, WalletLedgerEntry, Payout and PayoutProof persistence with immutable/version-aware fields. | Sprint 1 | Platform | Foundation | Database | Must | 8 | 8 | VKT-002 | BLOCKING | PLAN-001..007; WAL-001..007; §23 | Plan -> Subscription -> Invoice -> Payment -> Commission -> Ledger -> Payout.
VKT-005 | Task | Create AI/telephony/integration tables | Implement Agent, AgentTemplate, KnowledgeSource, PhoneNumber, Call, CallArtifact, IntegrationConnection, AgentAction, WebhookEndpoint and WebhookDelivery persistence. | Sprint 1 | Platform | Foundation | Database | Must | 8 | 8 | VKT-002 | BLOCKING | §23; AGT-001..008; TEL-001..010; INT-001..008; WH-001..008 | Customer -> Agent -> Number/Knowledge/Action/Integration -> Call/Artifacts.
VKT-006 | Task | Create notification and audit tables | Implement Notification and immutable AuditEvent storage with actor, role, tenant, action, entity, timestamp, correlation/request ID and sensitive-field redaction. | Sprint 1 | Platform | Foundation | Database | Must | 3 | 5 | VKT-003 | BLOCKING | NOT-001..005; AUD-001..005 | Business event -> notification/audit consumers; audit cannot be edited/deleted by ordinary UI.
VKT-007 | Task | Implement secure authentication/session foundation | Implement secure authentication for all three portals, secure session handling, logout, session invalidation and server-side authorization hooks. Support MFA capability for privileged roles where enabled. | Sprint 1 | Platform | Foundation | Authentication | Must | 5 | 8 | None | BLOCKING | SEC-001, SEC-006, RBAC-007..008 | Login -> authenticated session -> scoped portal -> logout/disable invalidates session.
VKT-008 | Task | Implement server-side RBAC and tenant guards | Every protected request must check role permissions and tenant ownership server-side. Agency roles cannot gain platform permissions; customer roles cannot gain agency permissions. | Sprint 1 | Platform | Foundation | Authorization | Must | 8 | 8 | VKT-003, VKT-007 | BLOCKING | TEN-001..005; SEC-002; RBAC-002..006 | Request -> authenticate -> resolve scope -> authorize -> execute/deny.
VKT-009 | Task | Implement input validation and security middleware | Normalize/validate URLs, phone numbers, webhook payloads and external inputs; add CSRF protection, rate limits and secure transport/session configuration. | Sprint 1 | Platform | Foundation | Security | Must | 5 | 7 | VKT-007, VKT-008 | BLOCKING | SEC-005..010 | External input -> validation -> normalized domain value -> service; rejected input returns stable error.
VKT-010 | Task | Implement server-side secret management | Store payment, telephony, AI, OAuth refresh and webhook signing secrets encrypted/secret-managed; never expose them to client code, prompts, transcripts or logs. | Sprint 1 | Platform | Foundation | Secrets | Must | 3 | 5 | VKT-009 | BLOCKING | SEC-003, SEC-015, INT-002 | Credential entry -> encrypted secret reference -> provider adapter; never return secret.
VKT-011 | Task | Define versioned API conventions and error contract | Create consistent versioned API conventions, pagination, stable machine-readable errors, human-readable messages and request/correlation IDs. | Sprint 1 | Platform | Foundation | API | Must | 3 | 5 | VKT-008, VKT-009 | BLOCKING | §30.1 | UI/provider -> API -> validation/auth -> service -> structured response/error.
VKT-012 | Task | Implement internal domain-event contract | Define idempotent internal events mirroring lifecycle semantics used for notifications, audit, reporting and outbound webhook delivery. | Sprint 1 | Platform | Foundation | Events | Must | 3 | 5 | VKT-006, VKT-011 | BLOCKING | §30.2; Appendix B | Domain transaction -> event_id/event_type -> idempotent consumers.
VKT-013 | Task | Implement canonical money, UTC and E.164 handling | Store monetary values in safe minor units/decimal with currency, timestamps in UTC, and phone numbers normalized to E.164 where applicable. | Sprint 1 | Platform | Foundation | Time/money/phone | Must | 3 | 4 | VKT-002, VKT-011 | BLOCKING | NFR-010..012 | Input -> canonical representation -> storage -> tenant/user timezone display.
VKT-014 | Task | Implement secure file upload abstraction | Provide type/size policy, private storage references and malware scanning where infrastructure permits for KYC/knowledge files; separate internal KYC visibility. | Sprint 1 | Platform | Foundation | File security | Must | 3 | 5 | VKT-009, VKT-010 | BLOCKING | KYC-002, KYC-005, SEC-011, PRIV-002 | Upload -> validate -> private storage -> hash/ref -> processing state.
VKT-015 | Task | Create production-like staging environment and CI checks | Create deployable staging configuration, database migration pipeline, automated test execution, secret injection and environment separation. Do not hard-code provider credentials. | Sprint 1 | Platform | Foundation | Environment | Must | 5 | 6 | VKT-010, VKT-011 | BLOCKING | NFR-004..007 | Commit -> CI -> tests -> migration checks -> staging deployment.
VKT-016 | Task | Build Super Admin application shell | Create authenticated Super Admin layout, navigation, route guards, permission-aware menu visibility and shared list/detail/form patterns. | Sprint 2 | Super Admin | Portal Shell | Layout & navigation | Must | 3 | 5 | VKT-007, VKT-008 | BLOCKING | §7; SEC-001..002 | Login -> Super Admin shell -> authorized module -> scoped data.
VKT-017 | Task | Build Super Admin dashboard | Display agencies, customers, agents, numbers, calls, minutes, MRR, payments, commission liability, pending payouts and KYC queue; add financial summary, operational health and drilldown/date filters. | Sprint 2 | Super Admin | Dashboard | Dashboard screen | Must | 5 | 7 | VKT-011, VKT-012, VKT-016 | PARALLEL | SA1-001..005 | Filter period -> KPI cards -> click card -> filtered module view.
VKT-018 | Task | Build agency directory with search/filter/status visibility | List agencies with status and key operational/commercial information; support platform-wide search/filter needed by admin workflows. | Sprint 2 | Super Admin | Agencies | Agency list screen | Must | 3 | 4 | VKT-003, VKT-016 | PARALLEL | SA2-001..008 | Dashboard/list -> search/filter -> agency detail.
VKT-019 | Task | Build Create Agency form | Create agency identity, owner/contact details, default status, commission rate, currency/region and optional operating restrictions. Creation starts Invited/Onboarding according to flow and sends secure owner invitation. | Sprint 2 | Super Admin | Agencies | Create agency screen | Must | 5 | 6 | VKT-018, VKT-011 | BLOCKING | SA2-001; §6.1 | Create Agency -> persist -> invitation -> agency owner onboarding.
VKT-020 | Task | Build agency profile/detail and resource tabs | Show/edit legal/operating data subject to audit rules; expose customers, agents, numbers, calls, integrations, team, knowledge and financial overview. | Sprint 2 | Super Admin | Agencies | Agency detail screen | Must | 5 | 6 | VKT-018, VKT-019 | BLOCKING | SA2-002, SA2-006, SA2-007 | Agency list -> detail -> resource tabs -> scoped records.
VKT-021 | Task | Implement commission rate/effective-date UI and service | Set/change commission rate with effective date. Historical commission records retain the original rate/rule snapshot. | Sprint 2 | Super Admin | Agencies | Commission control | Must | 3 | 5 | VKT-004, VKT-020 | BLOCKING | SA2-003; BR-001, BR-018 | Agency -> Commission -> effective date -> new transactions use new rate; old entries unchanged.
VKT-022 | Task | Implement agency status and capability overrides | Activate/restrict/suspend/reactivate/close agency and enable/disable customer creation, agent creation, number purchase, payout requests and other controlled capabilities. Require confirmation and audit. | Sprint 2 | Super Admin | Agencies | Status/capability controls | Must | 5 | 6 | VKT-006, VKT-020 | BLOCKING | SA2-004..005; BR-012..015 | Admin action -> impact warning where needed -> confirmation -> status/capability change -> audit/event.
VKT-023 | Task | Build internal notes/risk flags | Allow platform-only internal notes and risk flags without exposing them to agency/customer users. | Sprint 2 | Super Admin | Agencies | Risk/internal notes | Must | 2 | 3 | VKT-020, VKT-006 | PARALLEL | SA2-008 | Agency detail -> internal note/risk flag -> platform-only visibility.
VKT-024 | Task | Build agency-owner invitation acceptance | Secure invited owner flow: accept invitation, create credentials, verify email and accept platform terms before portal access. | Sprint 2 | Agency | Onboarding | Invitation acceptance screen | Must | 3 | 5 | VKT-019, VKT-007 | BLOCKING | §6.1 | Invitation -> credentials -> email verification -> terms -> Agency onboarding.
VKT-025 | Task | Build KYC business identity form | Capture legal/trading name, entity type, registration/incorporation number where applicable, incorporation/operating countries and business address. | Sprint 2 | Agency | KYC | Business profile screen | Must | 3 | 5 | VKT-014, VKT-024 | BLOCKING | §6.2; KYC-001..005 | KYC Not Started/Incomplete -> save -> Incomplete.
VKT-026 | Task | Build owner/controller information form | Capture required owner/controller information including full legal name, lawful/required DOB/nationality, residential address and ownership/control relationship. | Sprint 2 | Agency | KYC | Owner/controller screen | Must | 3 | 4 | VKT-025 | BLOCKING | §6.2 | KYC Incomplete -> owner/controller section -> save -> Incomplete.
VKT-027 | Task | Build identity/business/address evidence upload | Upload government ID, registration/incorporation evidence and proof of address where required; enforce secure file policy and preserve versions on resubmission. | Sprint 2 | Agency | KYC | Evidence upload screen | Must | 5 | 6 | VKT-014, VKT-025 | BLOCKING | §6.2; KYC-002, KYC-005 | Upload -> validation/private storage -> evidence attached -> preserve prior version.
VKT-028 | Task | Build payout details capture | Capture beneficiary name, account identifier, bank/provider details, country and currency. Keep payout method unusable until verification rules are satisfied. | Sprint 2 | Agency | KYC | Payout details screen | Must | 3 | 4 | VKT-025, VKT-014 | BLOCKING | §6.2; KYC-001 | KYC -> payout details -> verification_state -> unavailable until allowed.
VKT-029 | Task | Build declarations and KYC submission | Capture accuracy/beneficial ownership declarations where applicable, platform terms, acceptable use and privacy/recording acknowledgements. Lock application on submission. | Sprint 2 | Agency | KYC | Declarations & submit | Must | 3 | 4 | VKT-026, VKT-027, VKT-028 | BLOCKING | §6.1; KYC-003..004 | Incomplete -> declarations -> Submit -> Submitted -> Under Review.
VKT-030 | Task | Build KYC review queue | Filter KYC applications by status, age, country, agency and risk flags; expose only to authorized KYC/platform roles. | Sprint 2 | Super Admin | KYC | KYC queue screen | Must | 3 | 5 | VKT-029, VKT-016 | BLOCKING | SA4-001; KYC-002 | KYC submitted -> queue -> filter -> review detail.
VKT-031 | Task | Build secure evidence review and notes | Securely inspect submitted information/documents; support internal reviewer notes and agency-visible request notes without exposing internal notes. | Sprint 2 | Super Admin | KYC | KYC review detail | Must | 3 | 5 | VKT-030 | BLOCKING | SA4-002; KYC-002..003 | Queue -> review -> inspect evidence -> internal/external notes.
VKT-032 | Task | Implement Verify / Reject / More Information | Implement state machine transitions and structured reason codes plus optional notes. Preserve prior evidence/audit history on resubmission. | Sprint 2 | Super Admin | KYC | KYC decision actions | Must | 5 | 6 | VKT-031, VKT-006, VKT-012 | BLOCKING | SA4-003..005; §6.3; KYC-003..006 | Under Review -> Verified / Rejected / More Information Required; More Info -> agency resubmits -> Submitted.
VKT-033 | Task | Implement status/capability gates centrally | Centralize agency/customer status and capability rules so UI cannot bypass restrictions. Suspended agencies cannot create customers; KYC gates payout eligibility. | Sprint 2 | Platform | Onboarding | Agency/customer/portal gate service | Must | 5 | 6 | VKT-008, VKT-022, VKT-032 | BLOCKING | BR-011..014; §24 | Action -> central policy check -> allow/deny; API manipulation must not bypass.
VKT-034 | Task | Implement onboarding/KYC notification triggers | Implement agency invitation, KYC submitted/approved/rejected/more-info notification triggers through in-app/email channels with mandatory notices protected from preference disabling. | Sprint 2 | Platform | Notifications | Onboarding/KYC notifications | Must | 3 | 5 | VKT-006, VKT-012, VKT-032 | PARALLEL | NOT-001..005; §19 | Domain event -> notification template -> recipient -> delivery log where supported.
VKT-035 | Task | Build plan catalog list | List plans and versions with status and commercial terms; expose versioned immutable terms once used by active subscriptions. | Sprint 3 | Super Admin | Plans | Plan list screen | Must | 3 | 4 | VKT-004, VKT-016 | PARALLEL | SA11-001..004; PLAN-001 | Plans -> list -> version detail.
VKT-036 | Task | Implement plan CRUD/versioning and entitlements | Configure price, billing cycle, included minutes, top-ups, overage/hard stop, agent/number/concurrency limits and feature flags. Preserve version used by active subscriptions. | Sprint 3 | Super Admin | Plans | Plan create/edit/version screen | Must | 5 | 7 | VKT-035, VKT-004 | BLOCKING | PLAN-001..007 | Create/version -> publish -> assign -> active subscription locks version.
VKT-037 | Task | Build global customer directory | Search/filter customers by agency, status, plan, balance and activity; maintain tenant ownership. | Sprint 3 | Super Admin | Customers | Customer directory screen | Must | 3 | 4 | VKT-003, VKT-016 | PARALLEL | SA3-001 | Customers -> filters -> customer detail.
VKT-038 | Task | Implement Super Admin customer creation | Create customer under any agency and capture identity/service/commercial controls. Enforce permanently-banned/re-onboarding checks where applicable. | Sprint 3 | Super Admin | Customers | Create/manage customer screen | Must | 5 | 6 | VKT-033, VKT-037 | BLOCKING | SA3-002; §24; risk/chargeback rules | Agency -> create customer -> risk check -> customer Invited/Active per policy.
VKT-039 | Task | Implement customer plan assignment, ledger-backed balance adjustment and suspension | Assign/change plan with effective date; adjust minute/monetary balance only through ledger-backed entries; suspend customer independently when authorized. | Sprint 3 | Super Admin | Customers | Customer plan/balance/suspension actions | Must | 5 | 7 | VKT-036, VKT-004, VKT-006, VKT-038 | BLOCKING | SA3-003..005; BR-020 | Customer -> action -> policy/permission -> ledger/status -> audit.
VKT-040 | Task | Build Agency customer list and create flow | Agency can create a customer only when agency is Active and capability is enabled. Capture customer profile and invite owner/admin users. | Sprint 3 | Agency | Customers | Customer list/create screen | Must | 5 | 6 | VKT-033, VKT-038 | BLOCKING | AG2-001..005 | Agency -> Customers -> Create -> status/capability gate -> customer -> invitation.
VKT-041 | Task | Build agency customer detail | Show customer profile, service status, plan, agents, numbers, calls, knowledge, integrations, invoices and usage within agency scope. | Sprint 3 | Agency | Customers | Customer detail/resources screen | Must | 3 | 5 | VKT-040, VKT-008 | PARALLEL | AG2-003..005 | Customer list -> detail -> resource tabs.
VKT-042 | Task | Implement customer owner/admin invitation | Customer invitation email links to credential creation/activation; customer status supports Invited -> Active according to platform flow. | Sprint 3 | Customer | Onboarding | Customer invitation/activation | Must | 3 | 4 | VKT-040, VKT-034, VKT-007 | BLOCKING | AG2-002; CU8-001; §24.2 | Agency creates/invites -> customer accepts -> credentials -> portal.
VKT-043 | Task | Implement customer subscription and invoice lifecycle | Create customer subscription referencing plan version; create invoices with amount/currency/status/processor reference; support open/paid/failed/refunded states. | Sprint 3 | Platform | Billing | Subscription/invoice domain service | Must | 8 | 8 | VKT-036, VKT-038, VKT-004 | BLOCKING | §10.1..10.3; CU5-001 | Customer -> plan -> subscription -> invoice -> payment.
VKT-044 | Task | Implement hosted/tokenized payment integration boundary | Integrate payment processor through adapter/hosted fields where possible; never store raw card security codes. Handle processor success/failure references. | Sprint 3 | Platform | Billing | Payment processor adapter | Must | 8 | 8 | VKT-043, VKT-010 | BLOCKING | BR-002; SEC-004; §10.3 | Invoice -> processor -> success/failure -> Payment record.
VKT-045 | Task | Implement payment webhook handling | Process payment events idempotently using provider event ID/idempotency key; repeated webhook cannot double-settle invoice or create duplicate commission. | Sprint 3 | Platform | Billing | Payment webhook idempotency/reconciliation | Must | 5 | 7 | VKT-044, VKT-012 | BLOCKING | §28; §30; NFR-005 | Provider event -> signature validation -> idempotency -> payment state -> downstream event.
VKT-046 | Task | Implement commissionable revenue calculation | Calculate commission only for eligible net revenue using the agency rate/rule snapshot. Exclude tax/promotional/goodwill defaults and apply configurable pass-through rules. | Sprint 3 | Platform | Commission | Commission calculation service | Must | 5 | 7 | VKT-021, VKT-045 | BLOCKING | BR-003; BR-018; §10.4 | Paid payment -> eligible line items -> snapshot rate -> commission amount.
VKT-047 | Task | Implement independent commission holds | Create one commission entry per qualifying payment with earned_at and available_at = qualifying settlement + 15 days. Held funds remain unavailable; freezes/reversals override release. | Sprint 3 | Platform | Commission | 15-day hold scheduler/state transition | Must | 5 | 6 | VKT-046, VKT-004 | BLOCKING | BR-004..006; WAL-001, WAL-006 | Commission created On Hold -> date reached/no block -> Available; otherwise remain blocked.
VKT-048 | Task | Implement ledger entries and balance derivation | Implement Commission Earned, Hold Released, Reversal, Manual Credit/Debit, Payout Reserved/Paid, Rejected/Cancelled and Freeze semantics. Cached balance cannot be authoritative. | Sprint 3 | Platform | Wallet | Immutable wallet ledger service | Must | 8 | 8 | VKT-004, VKT-046 | BLOCKING | BR-020; §11.1..11.2; WAL-001..007 | Financial event -> immutable ledger entry -> reproducible wallet buckets.
VKT-049 | Task | Build Super Admin payments/invoices/reconciliation UI | View customer payments, processor state/allocation, invoices, refunds, disputes/chargebacks and ledger-backed manual adjustments with reason. | Sprint 3 | Super Admin | Billing | Payments/invoices screen | Must | 5 | 6 | VKT-043, VKT-044, VKT-048 | PARALLEL | SA12-001..005 | Payments -> detail -> refund/dispute/adjustment -> audit.
VKT-050 | Task | Build agency wallet and bucket visibility | Display pending, held, available, frozen, withdrawal-pending and lifetime-paid values with ledger history. | Sprint 3 | Super Admin | Wallet/Payouts | Wallet overview screen | Must | 3 | 5 | VKT-048, VKT-016 | PARALLEL | SA13-001 | Agency -> Wallet -> bucket summary -> ledger.
VKT-051 | Task | Build Agency wallet summary and ledger | Show held/available/frozen/pending withdrawal/lifetime paid plus every earning, reversal, adjustment, hold release and payout. | Sprint 3 | Agency | Wallet/Payouts | Wallet screen | Must | 3 | 5 | VKT-048, VKT-041 | PARALLEL | AG11-001..002 | Agency -> Wallet -> ledger detail.
VKT-052 | Task | Implement payout request validation and reservation | Validate KYC Verified, agency status, payout capability, payout method and available balance. Atomically reserve requested amount from Available to Withdrawal Pending. | Sprint 3 | Agency | Wallet/Payouts | Withdraw screen | Must | 5 | 7 | VKT-032, VKT-048, VKT-051 | BLOCKING | §11.3; WAL-002; KYC-001 | Wallet -> Withdraw -> validations -> amount -> atomic reserve -> Requested.
VKT-053 | Task | Build payout review queue and detail | Review requested payouts and risk/compliance context; support approve, reject, freeze and process transitions. | Sprint 3 | Super Admin | Wallet/Payouts | Payout queue/detail screen | Must | 5 | 6 | VKT-052, VKT-016 | BLOCKING | SA13-002..003; §11.3; §24.5 | Requested -> Under Review -> Approved/Rejected/Frozen -> Processing.
VKT-054 | Task | Implement private proof upload and Paid transition | Upload private internal payout proof, enter non-sensitive transaction reference, enforce proof-required setting when configured, then mark Paid. | Sprint 3 | Super Admin | Wallet/Payouts | Payout proof + mark paid | Must | 5 | 6 | VKT-053, VKT-014, VKT-006 | BLOCKING | SA13-004..005; BR-009..010 | Processing -> private proof -> transaction ref -> Paid.
VKT-055 | Task | Generate agency-visible payout receipt | Generate receipt number, agency name, request ID, amount/currency, masked method, request/paid dates, Paid status, masked/non-sensitive reference and issuer details. | Sprint 3 | Platform | Wallet/Payouts | Payout receipt generator | Must | 3 | 5 | VKT-054, VKT-012 | BLOCKING | §11.4; BR-010 | Mark Paid -> finalize ledger -> receipt -> agency notification.
VKT-056 | Task | Build agency payout history and receipt access | Agency can view/download generated receipts but cannot access private admin proof. | Sprint 3 | Agency | Wallet/Payouts | Payout history/receipt screen | Must | 3 | 4 | VKT-055, VKT-008 | BLOCKING | AG11-005; BR-009 | Wallet -> payouts -> Paid -> receipt; proof endpoint denied.
VKT-057 | Task | Implement commission reversal rules | Refund during hold reverses held commission; refund after availability debits available; pending payout may be reduced/cancelled/recalculated; paid commission creates negative balance/recovery from future earnings. Never rewrite history. | Sprint 3 | Platform | Billing/Commission | Refund/chargeback reversal service | Must | 8 | 8 | VKT-048, VKT-045, VKT-046 | BLOCKING | BR-017; §28; Appendix C | Refund/chargeback -> locate original commission -> state-specific reversal -> ledger/audit/event.
VKT-058 | Task | Implement confirmed chargeback customer freeze and re-onboarding prevention | Confirmed chargeback freezes the customer, immediately disables all customer agents and production calling, blocks new resources except approved recovery payments, creates a risk event, notifies responsible parties and blocks re-onboarding where permanently banned. | Sprint 3 | Platform | Risk | Customer chargeback freeze/re-onboarding rules | Must | 8 | 8 | VKT-057, VKT-006, VKT-012 | BLOCKING | Risk rules §§16-24; BR-017 | Chargeback -> customer frozen -> agents disabled -> onboarding blocked -> risk/audit/notifications.
VKT-059 | Task | Implement agency fraud/risk actions | Support freezing payouts/wallet, blocking customer/agent/number creation, requiring KYC/re-verification, investigation, suspension and termination while allowing existing services to be handled separately. | Sprint 3 | Platform | Risk | Agency fraud/risk controls | Must | 5 | 6 | VKT-022, VKT-058 | BLOCKING | Risk rules §§25-27 | Risk signal -> Super Admin action -> capability/status changes -> audit/notifications.
VKT-060 | Task | Implement billing/wallet notification triggers | Implement payment success/failure, low minutes, commission available, payout requested/paid/rejected and agency restriction/suspension notification triggers. | Sprint 3 | Platform | Notifications | Billing/wallet notifications | Must | 3 | 5 | VKT-012, VKT-047, VKT-055 | PARALLEL | §19; NOT-001..005 | Event -> recipient selection -> in-app/email -> preference enforcement.
VKT-061 | Task | Build global agent directory and diagnostics entry | List all agents by agency/customer/status/type/number; expose runtime configuration, recent calls, errors and integrations. | Sprint 4 | Super Admin | Agents | Agent directory | Must | 3 | 5 | VKT-005, VKT-016 | PARALLEL | SA5-001..003 | Agents -> filters -> detail/diagnostics.
VKT-062 | Task | Implement Super Admin agent lifecycle actions | Implement create/edit/pause/publish/clone/archive and immediate disable actions with permission checks and audit/history. | Sprint 4 | Super Admin | Agents | Lifecycle actions | Must | 5 | 6 | VKT-061, VKT-008 | BLOCKING | SA5-002..004; AGT-003 | Agent action -> validation -> state transition -> audit/event.
VKT-063 | Task | Build agency agent directory and creation entry | List customer agents within agency scope and start creation from scratch or an allowed template. | Sprint 4 | Agency | Agents | Agent list/create | Must | 3 | 5 | VKT-041, VKT-061 | BLOCKING | AG3-001 | Agency -> Agents -> Create -> source choice -> Draft.
VKT-064 | Task | Build Identity stage | Configure agent name, customer, use case/type, status and timezone. New agent begins Draft. | Sprint 4 | Agency | Agents | Agent Builder - Identity | Must | 2 | 3 | VKT-063 | BLOCKING | §12.2; AGT-001 | Create -> Identity -> save Draft.
VKT-065 | Task | Build Voice & Language stage | Configure provider, voice, language and supported speaking style/speed settings. | Sprint 4 | Agency | Agents | Agent Builder - Voice & Language | Must | 3 | 4 | VKT-064 | BLOCKING | §12.2 | Draft -> Voice/Language -> save configuration.
VKT-066 | Task | Build Persona/Instructions stage | Configure role, goals, constraints, greeting, fallback behavior and layered instruction fields while preserving deterministic precedence. | Sprint 4 | Agency | Agents | Agent Builder - Persona & Instructions | Must | 5 | 6 | VKT-064, VKT-070, VKT-071 | BLOCKING | §12.2; INS-001..004 | Draft -> instructions -> resolve Platform -> Template -> Agency -> Customer -> Agent.
VKT-067 | Task | Build Knowledge attachment stage | Select allowed global/agency/customer/agent sources and attach/detach them while enforcing retrieval scope. | Sprint 4 | Agency | Agents | Agent Builder - Knowledge | Must | 3 | 5 | VKT-064, VKT-072, VKT-073 | BLOCKING | §12.2; KB-001..004; AGT-007 | Builder -> Knowledge -> select sources -> attach -> resolved agent knowledge.
VKT-068 | Task | Build Call Handling stage | Configure inbound/outbound permissions, business hours, voicemail/fallback, silence/timeouts and interruption settings. | Sprint 4 | Agency | Agents | Agent Builder - Call Handling | Must | 3 | 5 | VKT-064 | BLOCKING | §12.2 | Builder -> Call Handling -> save -> publish preflight consumes settings.
VKT-069 | Task | Build Tools/Actions stage | Select explicitly allowed normalized actions and parameter schemas; only configured tools can execute. | Sprint 4 | Agency | Agents | Agent Builder - Tools/Actions | Must | 3 | 5 | VKT-064, VKT-088 | BLOCKING | §12.2; AGT-005; INT-003..004 | Builder -> Tools -> allowlist -> action schema -> runtime authorization.
VKT-070 | Task | Implement deterministic instruction inheritance/resolution | Enforce Platform Safety/Global -> Template/Base -> Agency -> Customer -> Agent precedence. Mandatory platform safety rules cannot be overridden. | Sprint 4 | Platform | Instructions | Instruction resolution | Must | 5 | 6 | VKT-008, VKT-006 | BLOCKING | §14.1; INS-001..004 | Resolve at runtime/build preview -> ordered layers -> final effective instructions.
VKT-071 | Task | Build global and template instruction management | Manage platform safety/behavior instructions and reusable template instructions with version/audit history. | Sprint 4 | Super Admin | Instructions | Global/template instruction screens | Must | 3 | 4 | VKT-070, VKT-016 | PARALLEL | SA7-001..004 | Admin -> Instructions -> edit/version -> audit -> available to agents/templates.
VKT-072 | Task | Build global knowledge source management | Create shared platform knowledge sources using supported source types and processing states. | Sprint 4 | Super Admin | Knowledge | Global knowledge screen | Must | 3 | 5 | VKT-014, VKT-016 | PARALLEL | SA8-001..004; KB-001..002 | Knowledge -> add source -> processing -> Ready/Failed/Stale.
VKT-073 | Task | Build agency-wide and customer-specific knowledge management | Create reusable agency knowledge and customer-specific sources; attach/detach sources to agents; enforce source ownership. | Sprint 4 | Agency | Knowledge | Agency/customer knowledge | Must | 5 | 6 | VKT-072, VKT-041 | BLOCKING | AG7-001..004; KB-001..004 | Agency/Customer -> Knowledge -> source -> processing -> attach to agent.
VKT-074 | Task | Implement knowledge processing states and failure-safe behavior | Support Queued, Processing, Ready, Failed and Stale/Needs Refresh. Failed ingestion must not break a published agent using last valid knowledge where safe. | Sprint 4 | Platform | Knowledge | Ingestion/processing | Must | 5 | 7 | VKT-014, VKT-073 | BLOCKING | KB-001..005; §28 | Upload/URL/Q&A -> queue -> processing -> Ready/Failed/Stale -> safe fallback to last valid source.
VKT-075 | Task | Build template catalog management UI | List/create/edit/version/archive reusable templates and expose metadata/visibility controls. | Sprint 4 | Super Admin | Templates | Template catalog screens | Must | 3 | 5 | VKT-005, VKT-016 | PARALLEL | SA6-001..004; TPL-001..005 | Templates -> list -> detail -> edit/version/archive.
VKT-076 | Task | Implement template metadata, visibility and versioning | Configure industry, use case, description, languages, default voice, instructions, recommended tools/knowledge, visibility and versions; revisions cannot silently alter deployed agents. | Sprint 4 | Super Admin | Templates | Template metadata/version/visibility | Must | 5 | 6 | VKT-075, VKT-071 | BLOCKING | TPL-001..005 | Create template -> version -> visibility -> publish.
VKT-077 | Task | Implement independent editable template installation | Agency installs allowed template and receives an independent editable agent configuration rather than a live shared dependency. | Sprint 4 | Agency | Templates | Install/clone template | Must | 3 | 5 | VKT-076, VKT-063 | BLOCKING | TPL-002, TPL-004 | Catalog -> Install -> visibility check -> clone configuration -> Draft agent.
VKT-078 | Task | Implement telephony provider abstraction | Create adapter boundary for number search/purchase/assignment/release and call routing so provider-specific fields do not leak into core business logic. | Sprint 4 | Platform | Telephony | Provider adapter | Must | 5 | 6 | VKT-011, VKT-010 | BLOCKING | TEL-001 | Core telephony -> adapter -> provider -> normalized result.
VKT-079 | Task | Build phone number search UI | Search available supported numbers by country/area/capability and show provider metadata needed for selection. | Sprint 4 | Agency | Phone Numbers | Number search screen | Must | 3 | 5 | VKT-078, VKT-008 | BLOCKING | TEL-002; AG4-001 | Phone Numbers -> search criteria -> provider -> available results.
VKT-080 | Task | Implement number purchase, assignment, release and provisioning states | Purchase only when tenant status, entitlement, payment/balance rules and provider success permit. Assign one active routing target. Release requires confirmation and impact warning. | Sprint 4 | Agency | Phone Numbers | Purchase/assignment/release | Must | 8 | 8 | VKT-079, VKT-033, VKT-078 | BLOCKING | TEL-003..010; AG4-001..004 | Search -> purchase -> Pending/Active/Failed -> assign -> release -> Releasing/Released.
VKT-081 | Task | Implement idempotent number purchase reconciliation | Detect provider success/local timeout or local/provider ambiguity and reconcile through provider query/import or escalation without duplicate purchase. | Sprint 4 | Platform | Telephony | Purchase reconciliation | Must | 3 | 5 | VKT-080, VKT-012 | BLOCKING | TEL-010; §28 | Purchase -> timeout/partial result -> provider reconciliation -> final state.
VKT-082 | Task | Build transfer destination/team management | Create verified/validated transfer destinations such as phone number, department, queue or supported SIP/client target. | Sprint 4 | Agency | Transfers | Destination/team screen | Must | 3 | 5 | VKT-078, VKT-008 | BLOCKING | XFER-001..002; AG6-001 | Transfers -> destination -> validation/verification -> active target.
VKT-083 | Task | Build transfer rules | Configure triggers, business hours, timeout/no-answer and fallback behavior, including conditional rules. | Sprint 4 | Agency | Transfers | Rules screen | Must | 3 | 5 | VKT-082, VKT-064 | BLOCKING | XFER-003..005; AG6-002 | Destination -> trigger -> business hours -> transfer -> fallback.
VKT-084 | Task | Build integration/action mapping stage | Map normalized agent actions to authorized CRM/automation/API connections; credentials remain hidden. | Sprint 4 | Agency | Agents | Agent Builder - Integrations | Must | 3 | 5 | VKT-069, VKT-086 | BLOCKING | §12.2; INT-001..008 | Builder -> Integration -> connection/action -> test -> save mapping.
VKT-085 | Task | Build Transfers, Phone Number and Compliance stages | Configure transfers, assigned phone number and compliance fields including recording disclosure, prohibited behavior and required disclaimers where configured. | Sprint 4 | Agency | Agents | Agent Builder - Transfers/Number/Compliance | Must | 5 | 6 | VKT-080, VKT-083, VKT-084 | BLOCKING | §12.2; TEL-005..006; XFER-003..005 | Builder -> Transfers -> Number -> Compliance -> preflight-ready configuration.
VKT-086 | Task | Implement integration ownership/OAuth/credential isolation | Support agency/customer-owned connections, OAuth where supported, encrypted refresh tokens, revocation and dependent-action disablement. | Sprint 4 | Platform | Integrations | Connection service | Must | 5 | 7 | VKT-010, VKT-008 | BLOCKING | INT-001..002, INT-008 | Connect -> OAuth/credential storage -> Active -> disconnect -> revoke/disable dependent actions.
VKT-087 | Task | Build integrations UI | Connect authorized HubSpot, Salesforce, Zoho, QuickBooks and configure n8n/Zapier/Make through webhook/API patterns; never display stored credentials/tokens. | Sprint 4 | Agency | Integrations | Connection screens | Must | 5 | 6 | VKT-086, VKT-041 | BLOCKING | AG8-001..005 | Integrations -> provider -> connect -> status -> test -> active/error.
VKT-088 | Task | Implement normalized action execution | Implement action schemas, timeout/error behavior, sanitized failures, provider rate limits and authorization so only configured actions execute. | Sprint 4 | Platform | Integrations | Normalized action runtime | Must | 8 | 8 | VKT-086, VKT-087, VKT-069 | BLOCKING | INT-003..007 | Agent -> normalized action -> connection -> provider/API -> sanitized result/error.
VKT-089 | Task | Build webhook endpoint management | Create/update/disable endpoints, subscribe to allowed events, generate/rotate tenant-specific signing secret and send safe test events. | Sprint 4 | Agency | Webhooks | Endpoint CRUD/subscription screens | Must | 5 | 6 | VKT-010, VKT-012, VKT-041 | BLOCKING | AG9-001..005; WH-001..005 | Webhooks -> endpoint -> event subscriptions -> secret -> test -> active.
VKT-090 | Task | Implement signed webhook delivery | Create unique delivery/event IDs, sign payloads, retry transient failures with bounded backoff, log status/attempts/timestamps, allow eligible replay and support synchronous agent/knowledge webhook patterns. | Sprint 4 | Platform | Webhooks | Signed delivery/retry/replay | Must | 8 | 8 | VKT-089, VKT-012, VKT-011 | BLOCKING | WH-001..008; §30.3 | Domain event -> scoped endpoint -> signed delivery -> response -> retry/replay.
VKT-091 | Task | Build browser/simulator test screen | Allow agent test/simulator execution with transcript and tool traces where enabled; Draft/Testing agents cannot receive production traffic. | Sprint 5 | Agency | Agents | Agent Builder - Test | Must | 5 | 7 | VKT-064, VKT-067, VKT-068, VKT-069, VKT-084, VKT-085 | BLOCKING | AG3-003; §12.2 | Builder -> Test -> simulator -> transcript/tool trace -> return to builder.
VKT-092 | Task | Implement agent publish validation | Before publish validate customer status, plan entitlement, number/routing, instructions, voice/provider and required compliance fields. | Sprint 5 | Platform | Agents | Publish preflight | Must | 5 | 7 | VKT-091, VKT-033, VKT-036, VKT-080, VKT-070 | BLOCKING | AGT-002 | Draft/Testing -> preflight -> pass -> Active; fail -> actionable validation errors and no production traffic.
VKT-093 | Task | Build publish, activate, pause and clone actions | Implement publish/activate/deactivate/pause and clone flows subject to status, entitlement and permissions. Published changes preserve audit/revision history. | Sprint 5 | Agency | Agents | Publish/lifecycle screen | Must | 3 | 5 | VKT-092, VKT-062 | BLOCKING | AG3-004..005; AGT-003..004 | Test -> Publish -> Active; Active -> Paused; configuration retained.
VKT-094 | Task | Implement call ingestion and lifecycle persistence | Record Vokit/provider IDs, tenant ownership, direction, caller/callee, timestamps, status/disconnect reason, duration and billable usage fields. | Sprint 5 | Platform | Calls | Call lifecycle | Must | 8 | 8 | VKT-078, VKT-093, VKT-005 | BLOCKING | CALL-001..002; §16.1 | Call started -> answered -> terminal state -> persisted Call.
VKT-095 | Task | Implement inbound routing to assigned agent/fallback | Route incoming calls to the assigned active agent and configured fallback; enforce agent/customer/agency state and provider policy. | Sprint 5 | Platform | Calls | Inbound routing | Must | 8 | 8 | VKT-080, VKT-093, VKT-094 | BLOCKING | TEL-004..006 | Inbound number -> assignment -> active agent -> call; otherwise configured fallback.
VKT-096 | Task | Implement outbound calling/caller ID where enabled | Support outbound agent calling where enabled by configuration/provider policy, using authorized caller ID and normalized number rules. | Sprint 5 | Platform | Calls | Outbound calling | Must | 5 | 6 | VKT-095, VKT-093 | BLOCKING | TEL-006; §2.1 | Agent outbound -> entitlement/config check -> authorized caller ID -> provider -> Call.
VKT-097 | Task | Implement billable usage and entitlement linkage | Calculate billable usage consistently and link usage to customer subscription/balance, plan allocation and overage/hard-stop behavior. | Sprint 5 | Platform | Calls | Usage charging | Must | 8 | 8 | VKT-094, VKT-043 | BLOCKING | CALL-002; PLAN-002..005 | Call duration -> billable units -> plan allocation/overage -> usage/balance.
VKT-098 | Task | Implement recording/transcript/summary artifact service | Persist recording/transcript/summary references and optional sentiment/outcome/tool activity; enforce role, tenant, legal configuration and retention metadata. | Sprint 5 | Platform | Calls | Artifacts | Must | 8 | 8 | VKT-094, VKT-014 | BLOCKING | CALL-003..005; PRIV-003..004 | Call completed -> artifacts ready -> permission check -> authorized viewer.
VKT-099 | Task | Implement transfer execution and call linkage | Execute configured transfer triggers/business hours/fallback; preserve context/whisper where supported and record transfer attempt/outcome in call record. | Sprint 5 | Platform | Transfers | Human handoff runtime | Must | 5 | 7 | VKT-083, VKT-095, VKT-094 | BLOCKING | XFER-003..007 | Call -> trigger -> destination -> connect/no-answer -> fallback -> call outcome.
VKT-100 | Task | Build Super Admin call monitoring | Search all calls by agency/customer/agent/number/date/status/direction; detail shows provider ID, timestamps, duration, billable units, artifacts and tool activity; platform cost is permission-gated. | Sprint 5 | Super Admin | Calls | Global call list/detail | Must | 5 | 6 | VKT-094, VKT-098, VKT-016 | PARALLEL | SA14-001..004 | Calls -> filters -> detail -> permission-gated artifacts/cost.
VKT-101 | Task | Build agency call monitoring | Agency-wide call list/detail with filters and recording/transcript/summary/outcome/tools where enabled, subject to customer agreement/platform privacy policy. | Sprint 5 | Agency | Calls | Agency call list/detail | Must | 3 | 5 | VKT-100, VKT-008 | BLOCKING | AG5-001..003 | Agency -> Calls -> filter -> detail -> privacy authorization.
VKT-102 | Task | Build Customer Portal shell | Create authenticated customer layout, responsive monitoring/basic-action navigation and customer-scope route guards. | Sprint 5 | Customer | Portal Shell | Layout/navigation | Must | 3 | 5 | VKT-042, VKT-008 | BLOCKING | §9; NFR-009 | Customer login -> shell -> customer-owned modules only.
VKT-103 | Task | Build Customer dashboard | Show agents, calls this month, minutes used/remaining, plan, invoice status, recent calls and service alerts for low minutes/payment due/agent offline/important notifications. | Sprint 5 | Customer | Dashboard | Dashboard | Must | 5 | 6 | VKT-097, VKT-043, VKT-102 | BLOCKING | CU1-001..002 | Login -> dashboard -> KPI/alert -> linked module.
VKT-104 | Task | Build customer agent monitoring | Show assigned agents, status, number and high-level configuration. Editing is disabled by default; only explicitly permitted actions/fields are available. | Sprint 5 | Customer | Agents | Agent list/detail | Must | 3 | 5 | VKT-093, VKT-102 | BLOCKING | CU2-001..003 | Customer -> Agents -> detail -> permission check -> optional pause/resume.
VKT-105 | Task | Build customer call history and artifacts | Show only customer-owned calls; filter by agent/number/date/direction/outcome; display recording/transcript/summary only if enabled/authorized; export only when permitted. | Sprint 5 | Customer | Calls | Call history/detail | Must | 5 | 6 | VKT-101, VKT-098, VKT-102 | BLOCKING | CU3-001..004 | Customer -> Calls -> filters -> detail -> artifact authorization.
VKT-106 | Task | Build customer usage and top-up screen | Show included, consumed, remaining and additional minutes; breakdown by agent/date where feasible; allow purchase of Vokit-offered additional minute packages. | Sprint 5 | Customer | Usage | Usage/minutes | Must | 5 | 6 | VKT-097, VKT-044, VKT-102 | BLOCKING | CU4-001..003 | Customer -> Usage -> balances/breakdown -> Top-up -> payment -> additional minutes.
VKT-107 | Task | Build customer invoices and payment UI | List open/paid/failed/refunded invoices; pay outstanding invoices through Vokit; add/update payment method through processor-hosted secure flow where possible; download receipts/invoices. | Sprint 5 | Customer | Billing | Invoices/payments | Must | 5 | 7 | VKT-043, VKT-044, VKT-102 | BLOCKING | CU5-001..004; SEC-004 | Customer -> Billing -> invoice -> pay -> processor -> Paid/Failed -> receipt.
VKT-108 | Task | Build customer knowledge view/edit where granted | View customer knowledge attached to agents; upload/edit only where agency explicitly grants permission. | Sprint 5 | Customer | Knowledge | Knowledge | Must | 3 | 4 | VKT-073, VKT-074, VKT-102 | PARALLEL | CU6-001..002 | Customer -> Knowledge -> source -> permission -> view/edit -> processing.
VKT-109 | Task | Build customer integration visibility and permitted self-service | Show integrations relevant to customer; allow customer-owned connection only when agency enables self-service. | Sprint 5 | Customer | Integrations | Integration status/self-service | Must | 3 | 4 | VKT-087, VKT-102 | PARALLEL | CU7-001..002 | Customer -> Integrations -> status -> if enabled connect customer-owned account.
VKT-110 | Task | Build customer team, notifications and profile settings | Invite/manage customer team by role; configure notification preferences; manage allowed business/contact settings. | Sprint 5 | Customer | Team/Settings | Team/settings | Must | 3 | 5 | VKT-102, VKT-008 | PARALLEL | CU8-001..003 | Customer -> Team/Settings -> permission -> update/invite.
VKT-111 | Task | Build agency team, notification and security settings | Invite/assign/revoke agency users within allowed roles; configure notification preferences, allowed profile/branding fields and sessions/password/MFA when supported. | Sprint 5 | Agency | Team/Settings | Team/settings | Must | 5 | 6 | VKT-008, VKT-034 | PARALLEL | AG13-001..003; AG14-001..003 | Agency -> Team/Settings -> invite/role/revoke; Preferences/Security updates.
VKT-112 | Task | Build Super Admin user and role management | Invite/disable platform users; create role/permission bundles; keep KYC, payout, wallet adjustment, commission edit and impersonation permissions explicit. | Sprint 5 | Super Admin | Users/Roles | Platform users/roles | Must | 5 | 6 | VKT-008, VKT-016 | BLOCKING | SA18-001..003 | Admin -> Users/Roles -> role bundle -> assign -> access enforced server-side.
VKT-113 | Task | Complete notification preference and template engine | Support in-app/email, validated template variables, escaped untrusted content, mandatory notice categories and delivery status where provider supports. | Sprint 5 | Platform | Notifications | Notification engine/preferences | Must | 5 | 7 | VKT-034, VKT-060, VKT-006 | BLOCKING | NOT-001..005 | Event -> preference check -> mandatory/non-mandatory -> render -> deliver -> log.
VKT-114 | Task | Build Super Admin notification administration | Manage system email/in-app templates, inspect delivery status where supported and send platform/agency-targeted announcements. | Sprint 5 | Super Admin | Notifications | Template/delivery/announcement screens | Must | 3 | 5 | VKT-113, VKT-016 | PARALLEL | SA16-001..003 | Admin -> Notifications -> template/delivery/announcement -> scoped recipients.
VKT-115 | Task | Build provider registry and tenant connection visibility | Configure available integration/provider strategy and inspect tenant connection status without exposing secrets; allow disabling compromised connections. | Sprint 6 | Super Admin | Integrations | Provider registry/connection visibility | Must | 3 | 5 | VKT-086, VKT-016 | PARALLEL | SA15-001..004 | Admin -> Providers/Connections -> status -> disable if compromised.
VKT-116 | Task | Build webhook delivery log and replay UI | Inspect endpoint, event, status, retries, timestamps and response codes/metadata; replay only eligible failed deliveries. | Sprint 6 | Super Admin | Webhooks | Webhook logs/replay | Must | 3 | 5 | VKT-090, VKT-016 | PARALLEL | SA15-003; WH-005..006 | Admin -> Webhooks -> delivery detail -> replay authorization -> signed resend.
VKT-117 | Task | Build transfer monitoring | View tenant transfer destinations/rules; disable unsafe/invalid targets and inspect failed transfers where supported. | Sprint 6 | Super Admin | Transfers | Transfer directory/diagnostics | Must | 3 | 4 | VKT-083, VKT-099 | PARALLEL | SA10-001..003 | Admin -> Transfers -> target/rule -> disable/diagnose -> audit.
VKT-118 | Task | Build immutable audit log search/detail | Search by actor, action, entity, tenant, IP/time and severity. Do not allow edit/delete. Redact secrets/full payment data/raw KYC content. | Sprint 6 | Super Admin | Audit | Audit log search/detail | Must | 3 | 5 | VKT-006, VKT-016 | BLOCKING | SA17-001..003; AUD-001..005 | Action -> AuditEvent -> searchable immutable record.
VKT-119 | Task | Implement Super Admin override workflow | Allow authorized overrides for agency/customer status, feature gates, agent status, number assignment, plan, KYC, payout eligibility/state, wallet freeze and commission rate. Require reason and production-call impact warning where applicable. | Sprint 6 | Super Admin | Overrides | High-risk override framework | Must | 5 | 7 | VKT-008, VKT-022, VKT-039, VKT-054, VKT-062, VKT-118 | BLOCKING | §21.1; BR-008; AUD-004..005 | Select override -> permission -> impact warning -> reason/confirmation -> state/ledger -> audit.
VKT-120 | Task | Build platform settings UI | Configure commercial, payout, telephony, AI, compliance, notifications, security and feature-flag settings listed by the SRS. | Sprint 6 | Super Admin | Settings | Platform settings | Must | 5 | 7 | VKT-010, VKT-016 | BLOCKING | §22 | Settings -> category -> validate -> save -> centralized config.
VKT-121 | Task | Implement centralized configurable business rules | Centralize hold duration, payout thresholds, commissionability, KYC gates, recording disclosure/retention, allowed countries/providers and other policy controls instead of duplicating them in UI code. | Sprint 6 | Platform | Settings | Business policy/config service | Must | 5 | 6 | VKT-120, VKT-033, VKT-047, VKT-046 | BLOCKING | NFR-014 | Module -> policy service -> current configured rule -> decision.
VKT-122 | Task | Implement configurable retention and deletion-request controls | Support retention for recordings, transcripts, logs, KYC and financial records subject to legal constraints; support customer/agency deletion requests with financial/KYC/legal exceptions. | Sprint 6 | Platform | Privacy | Retention/deletion workflow | Must | 5 | 7 | VKT-098, VKT-014, VKT-121, VKT-118 | BLOCKING | PRIV-001..006 | Policy -> retention metadata -> scheduled action -> deletion request -> exceptions -> audit.
VKT-123 | Task | Implement authorized tenant data export | Provide authorized operational data export where supported; enforce tenant scope and audit sensitive exports. | Sprint 6 | Platform | Privacy | Authorized data export | Must | 3 | 4 | VKT-008, VKT-118 | PARALLEL | PRIV-007; CALL-007 | Tenant request -> authorization -> scoped export -> audit.
VKT-124 | Task | Build platform operational/financial reporting | Report MRR, agencies, customers, agents, calls, minutes, failed payments, commission liability, held/available wallet, pending payouts, payout aging, KYC aging, provider costs and gross margin using authoritative data. | Sprint 6 | Super Admin | Reporting | Platform reports | Must | 5 | 7 | VKT-048, VKT-094, VKT-032, VKT-043 | BLOCKING | §29; RPT-001..005 | Reports -> period/timezone/tenant filters -> ledger/payment/call sources -> export where permitted.
VKT-125 | Task | Complete agency KPI/report data layer | Provide customer MRR, expected commission MRR, earned/held/available/lifetime paid, customers, agents, calls, minutes, top customers and payout status for agency dashboard. | Sprint 6 | Agency | Reporting | Agency dashboard data | Must | 3 | 5 | VKT-124, VKT-051 | PARALLEL | AG1-001..003; §29 | Agency dashboard -> scoped reporting query -> KPI/trend/alerts.
VKT-126 | Task | Complete customer KPI/report data layer | Provide plan, minutes used/remaining, call count/duration, agent activity, invoice/payment status and top-up history for customer views. | Sprint 6 | Customer | Reporting | Customer dashboard data | Must | 3 | 4 | VKT-124, VKT-103 | PARALLEL | CU1-001; §29 | Customer dashboard -> customer-scoped reporting query -> cards/lists.
VKT-127 | Task | Implement structured logs, metrics, traces and correlation IDs | Add observability for authentication, payments, commission/ledger, payout, KYC, telephony, webhooks, integrations and calls. Redact secrets and sensitive documents. | Sprint 6 | Platform | Observability | Critical workflow telemetry | Must | 5 | 6 | VKT-011, VKT-012, VKT-010 | BLOCKING | NFR-006; SEC-015 | Request/event -> correlation ID -> structured telemetry -> alerting.
VKT-128 | Task | Implement automated backups and recovery test | Configure automated database/configuration backup and execute a recovery validation sufficient for production release. | Sprint 6 | Platform | Reliability | Backup/recovery validation | Must | 3 | 5 | VKT-015, VKT-127 | BLOCKING | NFR-007 | Scheduled backup -> stored backup -> restore test -> documented result.
VKT-129 | Task | Automate commission/wallet/payout state transition tests | Cover payment success, independent 15-day holds, reversal during/after hold, payout reservation race, payout states, negative balance and corrective ledger behavior. | Sprint 6 | QA | Automated Tests | Financial state tests | Must | 8 | 8 | VKT-047, VKT-048, VKT-052, VKT-057 | BLOCKING | §31.2; WAL-001..007 | Arrange financial state -> event -> assert ledger/state/balance invariants.
VKT-130 | Task | Automate cross-tenant authorization tests | Verify agency cannot access another agency's customers/calls/agents/knowledge/wallet/payouts and customer cannot access other customer data; API manipulation cannot bypass restrictions. | Sprint 6 | QA | Automated Tests | Tenant isolation tests | Must | 8 | 7 | VKT-008, VKT-033, VKT-094 | BLOCKING | §31.2; TEN-001..005 | Actor A -> request tenant B ID -> deny/not-found without disclosure.
VKT-131 | Task | Automate payment/webhook/payout/number idempotency tests | Verify duplicate payment webhooks, duplicate payout requests/reservation races and irreversible number purchases do not double-apply. | Sprint 6 | QA | Automated Tests | Idempotency tests | Must | 8 | 7 | VKT-045, VKT-052, VKT-081, VKT-090 | BLOCKING | §31.2; NFR-005 | Duplicate event/request -> same outcome -> no duplicate side effect.
VKT-132 | Task | Run security checks for auth/RBAC/secrets/webhooks/uploads/payments | Validate secure sessions, CSRF, rate limits, secret isolation, inbound/outbound webhook signatures, upload controls, payment tokenization and log redaction. | Sprint 6 | QA | Security | Security test suite | Must | 8 | 8 | VKT-009, VKT-010, VKT-014, VKT-090, VKT-118 | BLOCKING | §25; §31.2 | Security test -> exploit attempt -> deny/secure result -> evidence.
VKT-133 | Task | Complete dashboard filter and drilldown behavior | Verify every dashboard card routes to the correct filtered module view and date filters support today, 7 days, 30 days, month-to-date and custom range. | Sprint 7 | Super Admin | UI Completion | Dashboard drilldowns/date filters | Must | 2 | 3 | VKT-017, VKT-124 | BLOCKING | SA1-004..005 | Dashboard -> filter -> KPI -> drilldown -> expected filtered list.
VKT-134 | Task | Complete Super Admin screens and permission-aware states | Finalize Agencies, Customers, KYC, Agents, Templates, Instructions, Knowledge, Phone Numbers, Transfers, Plans, Billing, Wallet/Payouts, Calls, Integrations/Webhooks, Notifications, Audit, Users/Roles and Settings with loading, empty, error and permission states. | Sprint 7 | Super Admin | UI Completion | All portal screens | Must | 5 | 8 | VKT-018, VKT-020, VKT-030, VKT-032, VKT-061, VKT-075, VKT-071, VKT-072, VKT-080, VKT-117, VKT-036, VKT-049, VKT-053, VKT-100, VKT-115, VKT-116, VKT-114, VKT-118, VKT-112, VKT-120 | BLOCKING | §7.1..7.19 | Module -> list -> detail/form -> action -> confirmation -> result/error -> audit/event where required.
VKT-135 | Task | Complete Agency portal screens and state/permission UX | Finalize Dashboard, Customers, Agents/Builder, Phone Numbers, Calls, Transfers, Knowledge, Integrations, Webhooks, Plans/Billing visibility, Wallet/Payouts, KYC, Team and Notifications/Settings including loading/empty/error/disabled states and status/capability messaging. | Sprint 7 | Agency | UI Completion | All portal screens | Must | 5 | 8 | VKT-040, VKT-063, VKT-091, VKT-093, VKT-079, VKT-101, VKT-082, VKT-073, VKT-087, VKT-089, VKT-051, VKT-052, VKT-056, VKT-029, VKT-111, VKT-125 | BLOCKING | §8.1..8.14 | Agency module -> scoped API -> permission/status gate -> screen -> action -> feedback.
VKT-136 | Task | Complete Customer portal screens and customer-scope UX | Finalize Dashboard, Agents, Calls, Usage/Minutes, Invoices/Payments, Knowledge, Integrations and Team/Settings with responsive behavior and customer-only data visibility. | Sprint 7 | Customer | UI Completion | All portal screens | Must | 5 | 8 | VKT-103, VKT-104, VKT-105, VKT-106, VKT-107, VKT-108, VKT-109, VKT-110, VKT-126 | BLOCKING | §9.1..9.8; TEN-005 | Customer module -> customer-scoped API -> permission -> screen/action -> feedback.
VKT-137 | Task | Verify payment and commission edge cases | Test repeated payment webhook, payment success with commission-write failure, refund during hold, refund after availability, chargeback after payout, commission-rate changes and payment-failure service rules. | Sprint 7 | Platform | Edge Cases | Payment/billing edge cases | Must | 5 | 6 | VKT-129, VKT-131, VKT-057 | BLOCKING | §28; Appendix C | Payment -> event/edge case -> idempotent/reconciled ledger outcome -> notifications/audit.
VKT-138 | Task | Verify payout and risk edge cases | Test agency suspension with requested payout, KYC expiry with available funds, accidental Paid state, missing proof, payout race conditions and negative balance recovery. | Sprint 7 | Platform | Edge Cases | Payout/risk edge cases | Must | 5 | 6 | VKT-129, VKT-119, VKT-054 | BLOCKING | §28; §24.5 | Risk/payout event -> policy gate -> state/ledger correction -> audit/notification.
VKT-139 | Task | Verify number/call/agent failure behavior | Test provider/local number purchase mismatch, customer out of minutes during call, integration timeout during call, knowledge ingestion failure, agent pause/error/fallback and active-call override warnings. | Sprint 7 | Platform | Edge Cases | Telephony/agent edge cases | Must | 5 | 7 | VKT-081, VKT-097, VKT-088, VKT-074, VKT-119 | BLOCKING | §28; AGT-008; TEL-010 | Runtime failure -> configured fallback/reconciliation -> safe continuation/disablement -> audit.
VKT-140 | Task | Run confirmed chargeback shutdown and re-onboarding prevention | Verify chargeback freezes customer, immediately disables all customer agents and production calling, blocks new minutes/numbers/agents/subscriptions/payment except approved recovery, notifies agency/Super Admin, reverses commission by state, and blocks re-onboarding across agencies where permanently banned. | Sprint 7 | Platform | Risk | Chargeback shutdown and ban | Must | 8 | 7 | VKT-058, VKT-059, VKT-137, VKT-139 | BLOCKING | Risk rules §§16-24; core rules summary | Chargeback -> customer freeze -> agent shutdown -> restrictions -> commission reversal -> risk/audit/notifications -> re-onboarding block.
VKT-141 | Task | Run complete agency lifecycle acceptance test | Create agency as Super Admin, send invitation, accept/create credentials, complete KYC, review/decision, verify activation and ensure payout remains blocked until KYC Verified. | Sprint 7 | QA | E2E | Agency onboarding/KYC | Must | 5 | 5 | VKT-019, VKT-024, VKT-029, VKT-032, VKT-033 | BLOCKING | §6.1; §31.1 | SA create -> invitation -> Agency onboarding/KYC -> review -> Verified -> Active.
VKT-142 | Task | Run customer commercial flow acceptance test | Create customer when agency is permitted, assign versioned plan, create invoice, pay Vokit directly, create exactly one commission with correct rate snapshot and 15-day availability date, activate entitlements and notifications. | Sprint 7 | QA | E2E | Customer/payment/commission | Must | 8 | 6 | VKT-040, VKT-043, VKT-044, VKT-046, VKT-047, VKT-060 | BLOCKING | §10.3; §31.1 | Agency -> Customer -> Plan -> Invoice -> Payment -> Commission On Hold -> entitlements.
VKT-143 | Task | Run telephony production-path acceptance test | Purchase/assign number, configure inbound routing, publish compliant agent, place inbound call, verify correct tenant/customer agent receives it and Call record/artifacts/usage are written according to configuration. | Sprint 7 | QA | E2E | Number/agent/call | Must | 8 | 6 | VKT-080, VKT-093, VKT-095, VKT-097, VKT-098 | BLOCKING | §15; §16; §31.1 | Number -> Agent -> Publish -> Inbound call -> Call record -> usage/artifacts.
VKT-144 | Task | Run tools, integration and human handoff acceptance test | Configure authorized integration/action and transfer destination/rules, test action execution with sanitized failures and verify transfer attempt/outcome is captured. | Sprint 7 | QA | E2E | Agent integration/transfer | Must | 5 | 5 | VKT-088, VKT-090, VKT-099 | BLOCKING | §17; §18; §31.1 | Agent -> action/transfer -> provider/integration -> result/fallback -> call/audit.
VKT-145 | Task | Verify customer portal scope and permitted functions | Confirm customer sees only owned agents/calls/invoices/usage, can pay invoices/top up where configured, and cannot access agency/platform data or restricted agent fields. | Sprint 7 | QA | E2E | Customer portal isolation | Must | 5 | 5 | VKT-136, VKT-130, VKT-107 | BLOCKING | §9; TEN-005; §31.1 | Customer login -> scoped data -> permitted action -> cross-tenant attempt denied.
VKT-146 | Task | Run payout request-to-receipt acceptance test | Verify only Available funds can be requested, atomic reservation occurs, admin review/actions work, private proof remains inaccessible to agency, Paid generates receipt and notification. | Sprint 7 | QA | E2E | Payout lifecycle | Must | 8 | 5 | VKT-052, VKT-053, VKT-054, VKT-055, VKT-056 | BLOCKING | §11.3; §11.4; §31.1 | Available -> Withdraw -> Requested -> Review -> Approved -> Processing -> proof -> Paid -> receipt.
VKT-147 | Task | Execute requirement-by-requirement Must regression | Run traceable regression covering all Must requirements in the SRS, with failures linked to exact requirement IDs and no scope additions. | Sprint 7 | QA | Release | Must-requirement regression | Must | 8 | 8 | VKT-129, VKT-130, VKT-131, VKT-132, VKT-141, VKT-142, VKT-143, VKT-144, VKT-145, VKT-146 | BLOCKING | All Must requirements | Requirement -> test -> pass/fail -> defect -> retest.
VKT-148 | Task | Verify SRS functional and engineering/QA release gates | Verify agency/KYC/customer/payment/commission/wallet/payout, suspension, telephony, customer scope, signed integrations/webhooks, reversal, roles, automated tests and security review gates. | Sprint 7 | QA | Release | Release gate verification | Must | 5 | 5 | VKT-147 | BLOCKING | §31.1; §31.2 | Release checklist -> evidence -> gate pass/fail -> sign-off.
VKT-149 | Task | Prepare production configuration and operational runbook | Configure providers, currencies, business-day/payout settings, compliance/retention settings, feature flags, notification sender and operational runbook without hard-coded secrets. Document unresolved jurisdiction/legal dependencies. | Sprint 7 | Operations | Release | Production configuration/runbook | Must | 5 | 6 | VKT-120, VKT-121, VKT-127, VKT-128, VKT-148 | BLOCKING | §22; §26; NFR-006..007 | Staging config -> reviewed production config -> secrets -> smoke test -> runbook.
VKT-150 | Task | Deploy V1 and validate critical production paths | Deploy the release, run smoke tests for authentication, tenancy, agency/KYC gate, customer creation, payment/commission, payout controls, number/agent/call routing and customer isolation. Confirm rollback readiness. | Sprint 7 | Operations | Release | Production deployment/smoke/rollback | Must | 5 | 6 | VKT-149 | BLOCKING | §31; NFR-001..007 | Deploy -> smoke -> monitor -> accept or rollback.
VKT-151 | Task | Close release with explicit V1 boundary | Record Product, Engineering, QA, Finance/Operations and Compliance/Legal sign-off. Confirm explicitly deferred capabilities remain outside V1. | Sprint 7 | Product/QA | Release | Final baseline sign-off/deferred scope | Must | 2 | 3 | VKT-150 | BLOCKING | §2.2; §32; SRS Baseline Sign-off | Release gates pass -> sign-off -> production baseline; deferred items remain outside V1.

## Full Task Register
Task ID | Sprint / Day | Portal / Layer | Epic | Module | Jira Task | Description / Definition of Done | Flow | Dependencies | Dependency Category | Est. Hours | Story Points | SRS Traceability | Priority
VKT-001 | Sprint 1 | Platform | Foundation | Architecture | Baseline implementation traceability | Create the implementation traceability matrix from every SRS module, requirement ID, state machine, event and release gate to Jira epics/tasks. Treat SRS business rules and state machines as authoritative. | SRS -> Jira Epic/Task -> API -> UI -> QA acceptance criterion. | None | BLOCKING | 3 | 2 | SRS §Document Governance; §31 | Must
VKT-002 | Sprint 1 | Platform | Foundation | Domain model | Define tenant ownership model | Define platform/agency/customer/agent/financial ownership relationships and enforce the rule that customer-owned objects retain both customer and agency ownership where required. | Platform -> Agency -> Customer -> Agent; Financial transaction links platform/agency/customer. | None | BLOCKING | 6 | 5 | TEN-001..006; §23 | Must
VKT-003 | Sprint 1 | Platform | Foundation | Database | Create core identity and tenancy tables | Implement Agency, Customer, User and Role persistence with status fields and scope boundaries. Do not allow financial/KYC/audit records to be hard-deleted through normal flows. | Create tenant -> assign owner -> assign scoped role -> persist status/ownership. | VKT-002 | BLOCKING | 7 | 5 | §23; TEN-001..006; RBAC-001..006 | Must
VKT-004 | Sprint 1 | Platform | Foundation | Database | Create commercial and financial tables | Implement Plan/version, Subscription, Invoice, Payment, CommissionEntry, WalletLedgerEntry, Payout and PayoutProof persistence with immutable/version-aware fields. | Plan -> Subscription -> Invoice -> Payment -> Commission -> Ledger -> Payout. | VKT-002 | BLOCKING | 8 | 8 | PLAN-001..007; WAL-001..007; §23 | Must
VKT-005 | Sprint 1 | Platform | Foundation | Database | Create AI/telephony/integration tables | Implement Agent, AgentTemplate, KnowledgeSource, PhoneNumber, Call, CallArtifact, IntegrationConnection, AgentAction, WebhookEndpoint and WebhookDelivery persistence. | Customer -> Agent -> Number/Knowledge/Action/Integration -> Call/Artifacts. | VKT-002 | BLOCKING | 8 | 8 | §23; AGT-001..008; TEL-001..010; INT-001..008; WH-001..008 | Must
VKT-006 | Sprint 1 | Platform | Foundation | Database | Create notification and audit tables | Implement Notification and immutable AuditEvent storage with actor, role, tenant, action, entity, timestamp, correlation/request ID and sensitive-field redaction. | Business event -> notification/audit consumers; audit cannot be edited/deleted by ordinary UI. | VKT-003 | BLOCKING | 5 | 3 | NOT-001..005; AUD-001..005 | Must
VKT-007 | Sprint 1 | Platform | Foundation | Authentication | Implement secure authentication/session foundation | Implement secure authentication for all three portals, secure session handling, logout, session invalidation and server-side authorization hooks. Support MFA capability for privileged roles where enabled. | Login -> authenticated session -> scoped portal -> logout/disable invalidates session. | None | BLOCKING | 8 | 5 | SEC-001, SEC-006, RBAC-007..008 | Must
VKT-008 | Sprint 1 | Platform | Foundation | Authorization | Implement server-side RBAC and tenant guards | Every protected request must check role permissions and tenant ownership server-side. Agency roles cannot gain platform permissions; customer roles cannot gain agency permissions. | Request -> authenticate -> resolve scope -> authorize -> execute/deny. | VKT-003, VKT-007 | BLOCKING | 8 | 8 | TEN-001..005; SEC-002; RBAC-002..006 | Must
VKT-009 | Sprint 1 | Platform | Foundation | Security | Implement input validation and security middleware | Normalize/validate URLs, phone numbers, webhook payloads and external inputs; add CSRF protection, rate limits and secure transport/session configuration. | External input -> validation -> normalized domain value -> service; rejected input returns stable error. | VKT-007, VKT-008 | BLOCKING | 7 | 5 | SEC-005..010 | Must
VKT-010 | Sprint 1 | Platform | Foundation | Secrets | Implement server-side secret management | Store payment, telephony, AI, OAuth refresh and webhook signing secrets encrypted/secret-managed; never expose them to client code, prompts, transcripts or logs. | Credential entry -> encrypted secret reference -> provider adapter; never return secret. | VKT-009 | BLOCKING | 5 | 3 | SEC-003, SEC-015, INT-002 | Must
VKT-011 | Sprint 1 | Platform | Foundation | API | Define versioned API conventions and error contract | Create consistent versioned API conventions, pagination, stable machine-readable errors, human-readable messages and request/correlation IDs. | UI/provider -> API -> validation/auth -> service -> structured response/error. | VKT-008, VKT-009 | BLOCKING | 5 | 3 | §30.1 | Must
VKT-012 | Sprint 1 | Platform | Foundation | Events | Implement internal domain-event contract | Define idempotent internal events mirroring lifecycle semantics used for notifications, audit, reporting and outbound webhook delivery. | Domain transaction -> event_id/event_type -> idempotent consumers. | VKT-006, VKT-011 | BLOCKING | 5 | 3 | §30.2; Appendix B | Must
VKT-013 | Sprint 1 | Platform | Foundation | Time/money/phone | Implement canonical money, UTC and E.164 handling | Store monetary values in safe minor units/decimal with currency, timestamps in UTC, and phone numbers normalized to E.164 where applicable. | Input -> canonical representation -> storage -> tenant/user timezone display. | VKT-002, VKT-011 | BLOCKING | 4 | 3 | NFR-010..012 | Must
VKT-014 | Sprint 1 | Platform | Foundation | File security | Implement secure file upload abstraction | Provide type/size policy, private storage references and malware scanning where infrastructure permits for KYC/knowledge files; separate internal KYC visibility. | Upload -> validate -> private storage -> hash/ref -> processing state. | VKT-009, VKT-010 | BLOCKING | 5 | 3 | KYC-002, KYC-005, SEC-011, PRIV-002 | Must
VKT-015 | Sprint 1 | Platform | Foundation | Environment | Create production-like staging environment and CI checks | Create deployable staging configuration, database migration pipeline, automated test execution, secret injection and environment separation. Do not hard-code provider credentials. | Commit -> CI -> tests -> migration checks -> staging deployment. | VKT-010, VKT-011 | BLOCKING | 6 | 5 | NFR-004..007 | Must
VKT-016 | Sprint 2 | Super Admin | Portal Shell | Layout & navigation | Build Super Admin application shell | Create authenticated Super Admin layout, navigation, route guards, permission-aware menu visibility and shared list/detail/form patterns. | Login -> Super Admin shell -> authorized module -> scoped data. | VKT-007, VKT-008 | BLOCKING | 5 | 3 | §7; SEC-001..002 | Must
VKT-017 | Sprint 2 | Super Admin | Dashboard | Dashboard screen | Build Super Admin dashboard | Display agencies, customers, agents, numbers, calls, minutes, MRR, payments, commission liability, pending payouts and KYC queue; add financial summary, operational health and drilldown/date filters. | Filter period -> KPI cards -> click card -> filtered module view. | VKT-011, VKT-012, VKT-016 | PARALLEL | 7 | 5 | SA1-001..005 | Must
VKT-018 | Sprint 2 | Super Admin | Agencies | Agency list screen | Build agency directory with search/filter/status visibility | List agencies with status and key operational/commercial information; support platform-wide search/filter needed by admin workflows. | Dashboard/list -> search/filter -> agency detail. | VKT-003, VKT-016 | PARALLEL | 4 | 3 | SA2-001..008 | Must
VKT-019 | Sprint 2 | Super Admin | Agencies | Create agency screen | Build Create Agency form | Create agency identity, owner/contact details, default status, commission rate, currency/region and optional operating restrictions. Creation starts Invited/Onboarding according to flow and sends secure owner invitation. | Create Agency -> persist -> invitation -> agency owner onboarding. | VKT-018, VKT-011 | BLOCKING | 6 | 5 | SA2-001; §6.1 | Must
VKT-020 | Sprint 2 | Super Admin | Agencies | Agency detail screen | Build agency profile/detail and resource tabs | Show/edit legal/operating data subject to audit rules; expose customers, agents, numbers, calls, integrations, team, knowledge and financial overview. | Agency list -> detail -> resource tabs -> scoped records. | VKT-018, VKT-019 | BLOCKING | 6 | 5 | SA2-002, SA2-006, SA2-007 | Must
VKT-021 | Sprint 2 | Super Admin | Agencies | Commission control | Implement commission rate/effective-date UI and service | Set/change commission rate with effective date. Historical commission records retain the original rate/rule snapshot. | Agency -> Commission -> effective date -> new transactions use new rate; old entries unchanged. | VKT-004, VKT-020 | BLOCKING | 5 | 3 | SA2-003; BR-001, BR-018 | Must
VKT-022 | Sprint 2 | Super Admin | Agencies | Status/capability controls | Implement agency status and capability overrides | Activate/restrict/suspend/reactivate/close agency and enable/disable customer creation, agent creation, number purchase, payout requests and other controlled capabilities. Require confirmation and audit. | Admin action -> impact warning where needed -> confirmation -> status/capability change -> audit/event. | VKT-006, VKT-020 | BLOCKING | 6 | 5 | SA2-004..005; BR-012..015 | Must
VKT-023 | Sprint 2 | Super Admin | Agencies | Risk/internal notes | Build internal notes/risk flags | Allow platform-only internal notes and risk flags without exposing them to agency/customer users. | Agency detail -> internal note/risk flag -> platform-only visibility. | VKT-020, VKT-006 | PARALLEL | 3 | 2 | SA2-008 | Must
VKT-024 | Sprint 2 | Agency | Onboarding | Invitation acceptance screen | Build agency-owner invitation acceptance | Secure invited owner flow: accept invitation, create credentials, verify email and accept platform terms before portal access. | Invitation -> credentials -> email verification -> terms -> Agency onboarding. | VKT-019, VKT-007 | BLOCKING | 5 | 3 | §6.1 | Must
VKT-025 | Sprint 2 | Agency | KYC | Business profile screen | Build KYC business identity form | Capture legal/trading name, entity type, registration/incorporation number where applicable, incorporation/operating countries and business address. | KYC Not Started/Incomplete -> save -> Incomplete. | VKT-014, VKT-024 | BLOCKING | 5 | 3 | §6.2; KYC-001..005 | Must
VKT-026 | Sprint 2 | Agency | KYC | Owner/controller screen | Build owner/controller information form | Capture required owner/controller information including full legal name, lawful/required DOB/nationality, residential address and ownership/control relationship. | KYC Incomplete -> owner/controller section -> save -> Incomplete. | VKT-025 | BLOCKING | 4 | 3 | §6.2 | Must
VKT-027 | Sprint 2 | Agency | KYC | Evidence upload screen | Build identity/business/address evidence upload | Upload government ID, registration/incorporation evidence and proof of address where required; enforce secure file policy and preserve versions on resubmission. | Upload -> validation/private storage -> evidence attached -> preserve prior version. | VKT-014, VKT-025 | BLOCKING | 6 | 5 | §6.2; KYC-002, KYC-005 | Must
VKT-028 | Sprint 2 | Agency | KYC | Payout details screen | Build payout details capture | Capture beneficiary name, account identifier, bank/provider details, country and currency. Keep payout method unusable until verification rules are satisfied. | KYC -> payout details -> verification_state -> unavailable until allowed. | VKT-025, VKT-014 | BLOCKING | 4 | 3 | §6.2; KYC-001 | Must
VKT-029 | Sprint 2 | Agency | KYC | Declarations & submit | Build declarations and KYC submission | Capture accuracy/beneficial ownership declarations where applicable, platform terms, acceptable use and privacy/recording acknowledgements. Lock application on submission. | Incomplete -> declarations -> Submit -> Submitted -> Under Review. | VKT-026, VKT-027, VKT-028 | BLOCKING | 4 | 3 | §6.1; KYC-003..004 | Must
VKT-030 | Sprint 2 | Super Admin | KYC | KYC queue screen | Build KYC review queue | Filter KYC applications by status, age, country, agency and risk flags; expose only to authorized KYC/platform roles. | KYC submitted -> queue -> filter -> review detail. | VKT-029, VKT-016 | BLOCKING | 5 | 3 | SA4-001; KYC-002 | Must
VKT-031 | Sprint 2 | Super Admin | KYC | KYC review detail | Build secure evidence review and notes | Securely inspect submitted information/documents; support internal reviewer notes and agency-visible request notes without exposing internal notes. | Queue -> review -> inspect evidence -> internal/external notes. | VKT-030 | BLOCKING | 5 | 3 | SA4-002; KYC-002..003 | Must
VKT-032 | Sprint 2 | Super Admin | KYC | KYC decision actions | Implement Verify / Reject / More Information | Implement state machine transitions and structured reason codes plus optional notes. Preserve prior evidence/audit history on resubmission. | Under Review -> Verified / Rejected / More Information Required; More Info -> agency resubmits -> Submitted. | VKT-031, VKT-006, VKT-012 | BLOCKING | 6 | 5 | SA4-003..005; §6.3; KYC-003..006 | Must
VKT-033 | Sprint 2 | Platform | Onboarding | Agency/customer/portal gate service | Implement status/capability gates centrally | Centralize agency/customer status and capability rules so UI cannot bypass restrictions. Suspended agencies cannot create customers; KYC gates payout eligibility. | Action -> central policy check -> allow/deny; API manipulation must not bypass. | VKT-008, VKT-022, VKT-032 | BLOCKING | 6 | 5 | BR-011..014; §24 | Must
VKT-034 | Sprint 2 | Platform | Notifications | Onboarding/KYC notifications | Implement onboarding/KYC notification triggers | Implement agency invitation, KYC submitted/approved/rejected/more-info notification triggers through in-app/email channels with mandatory notices protected from preference disabling. | Domain event -> notification template -> recipient -> delivery log where supported. | VKT-006, VKT-012, VKT-032 | PARALLEL | 5 | 3 | NOT-001..005; §19 | Must
VKT-035 | Sprint 3 | Super Admin | Plans | Plan list screen | Build plan catalog list | List plans and versions with status and commercial terms; expose versioned immutable terms once used by active subscriptions. | Plans -> list -> version detail. | VKT-004, VKT-016 | PARALLEL | 4 | 3 | SA11-001..004; PLAN-001 | Must
VKT-036 | Sprint 3 | Super Admin | Plans | Plan create/edit/version screen | Implement plan CRUD/versioning and entitlements | Configure price, billing cycle, included minutes, top-ups, overage/hard stop, agent/number/concurrency limits and feature flags. Preserve version used by active subscriptions. | Create/version -> publish -> assign -> active subscription locks version. | VKT-035, VKT-004 | BLOCKING | 7 | 5 | PLAN-001..007 | Must
VKT-037 | Sprint 3 | Super Admin | Customers | Customer directory screen | Build global customer directory | Search/filter customers by agency, status, plan, balance and activity; maintain tenant ownership. | Customers -> filters -> customer detail. | VKT-003, VKT-016 | PARALLEL | 4 | 3 | SA3-001 | Must
VKT-038 | Sprint 3 | Super Admin | Customers | Create/manage customer screen | Implement Super Admin customer creation | Create customer under any agency and capture identity/service/commercial controls. Enforce permanently-banned/re-onboarding checks where applicable. | Agency -> create customer -> risk check -> customer Invited/Active per policy. | VKT-033, VKT-037 | BLOCKING | 6 | 5 | SA3-002; §24; risk/chargeback rules | Must
VKT-039 | Sprint 3 | Super Admin | Customers | Customer plan/balance/suspension actions | Implement customer plan assignment, ledger-backed balance adjustment and suspension | Assign/change plan with effective date; adjust minute/monetary balance only through ledger-backed entries; suspend customer independently when authorized. | Customer -> action -> policy/permission -> ledger/status -> audit. | VKT-036, VKT-004, VKT-006, VKT-038 | BLOCKING | 7 | 5 | SA3-003..005; BR-020 | Must
VKT-040 | Sprint 3 | Agency | Customers | Customer list/create screen | Build Agency customer list and create flow | Agency can create a customer only when agency is Active and capability is enabled. Capture customer profile and invite owner/admin users. | Agency -> Customers -> Create -> status/capability gate -> customer -> invitation. | VKT-033, VKT-038 | BLOCKING | 6 | 5 | AG2-001..005 | Must
VKT-041 | Sprint 3 | Agency | Customers | Customer detail/resources screen | Build agency customer detail | Show customer profile, service status, plan, agents, numbers, calls, knowledge, integrations, invoices and usage within agency scope. | Customer list -> detail -> resource tabs. | VKT-040, VKT-008 | PARALLEL | 5 | 3 | AG2-003..005 | Must
VKT-042 | Sprint 3 | Customer | Onboarding | Customer invitation/activation | Implement customer owner/admin invitation | Customer invitation email links to credential creation/activation; customer status supports Invited -> Active according to platform flow. | Agency creates/invites -> customer accepts -> credentials -> portal. | VKT-040, VKT-034, VKT-007 | BLOCKING | 4 | 3 | AG2-002; CU8-001; §24.2 | Must
VKT-043 | Sprint 3 | Platform | Billing | Subscription/invoice domain service | Implement customer subscription and invoice lifecycle | Create customer subscription referencing plan version; create invoices with amount/currency/status/processor reference; support open/paid/failed/refunded states. | Customer -> plan -> subscription -> invoice -> payment. | VKT-036, VKT-038, VKT-004 | BLOCKING | 8 | 8 | §10.1..10.3; CU5-001 | Must
VKT-044 | Sprint 3 | Platform | Billing | Payment processor adapter | Implement hosted/tokenized payment integration boundary | Integrate payment processor through adapter/hosted fields where possible; never store raw card security codes. Handle processor success/failure references. | Invoice -> processor -> success/failure -> Payment record. | VKT-043, VKT-010 | BLOCKING | 8 | 8 | BR-002; SEC-004; §10.3 | Must
VKT-045 | Sprint 3 | Platform | Billing | Payment webhook idempotency/reconciliation | Implement payment webhook handling | Process payment events idempotently using provider event ID/idempotency key; repeated webhook cannot double-settle invoice or create duplicate commission. | Provider event -> signature validation -> idempotency -> payment state -> downstream event. | VKT-044, VKT-012 | BLOCKING | 7 | 5 | §28; §30; NFR-005 | Must
VKT-046 | Sprint 3 | Platform | Commission | Commission calculation service | Implement commissionable revenue calculation | Calculate commission only for eligible net revenue using the agency rate/rule snapshot. Exclude tax/promotional/goodwill defaults and apply configurable pass-through rules. | Paid payment -> eligible line items -> snapshot rate -> commission amount. | VKT-021, VKT-045 | BLOCKING | 7 | 5 | BR-003; BR-018; §10.4 | Must
VKT-047 | Sprint 3 | Platform | Commission | 15-day hold scheduler/state transition | Implement independent commission holds | Create one commission entry per qualifying payment with earned_at and available_at = qualifying settlement + 15 days. Held funds remain unavailable; freezes/reversals override release. | Commission created On Hold -> date reached/no block -> Available; otherwise remain blocked. | VKT-046, VKT-004 | BLOCKING | 6 | 5 | BR-004..006; WAL-001, WAL-006 | Must
VKT-048 | Sprint 3 | Platform | Wallet | Immutable wallet ledger service | Implement ledger entries and balance derivation | Implement Commission Earned, Hold Released, Reversal, Manual Credit/Debit, Payout Reserved/Paid, Rejected/Cancelled and Freeze semantics. Cached balance cannot be authoritative. | Financial event -> immutable ledger entry -> reproducible wallet buckets. | VKT-004, VKT-046 | BLOCKING | 8 | 8 | BR-020; §11.1..11.2; WAL-001..007 | Must
VKT-049 | Sprint 3 | Super Admin | Billing | Payments/invoices screen | Build Super Admin payments/invoices/reconciliation UI | View customer payments, processor state/allocation, invoices, refunds, disputes/chargebacks and ledger-backed manual adjustments with reason. | Payments -> detail -> refund/dispute/adjustment -> audit. | VKT-043, VKT-044, VKT-048 | PARALLEL | 6 | 5 | SA12-001..005 | Must
VKT-050 | Sprint 3 | Super Admin | Wallet/Payouts | Wallet overview screen | Build agency wallet and bucket visibility | Display pending, held, available, frozen, withdrawal-pending and lifetime-paid values with ledger history. | Agency -> Wallet -> bucket summary -> ledger. | VKT-048, VKT-016 | PARALLEL | 5 | 3 | SA13-001 | Must
VKT-051 | Sprint 3 | Agency | Wallet/Payouts | Wallet screen | Build Agency wallet summary and ledger | Show held/available/frozen/pending withdrawal/lifetime paid plus every earning, reversal, adjustment, hold release and payout. | Agency -> Wallet -> ledger detail. | VKT-048, VKT-041 | PARALLEL | 5 | 3 | AG11-001..002 | Must
VKT-052 | Sprint 3 | Agency | Wallet/Payouts | Withdraw screen | Implement payout request validation and reservation | Validate KYC Verified, agency status, payout capability, payout method and available balance. Atomically reserve requested amount from Available to Withdrawal Pending. | Wallet -> Withdraw -> validations -> amount -> atomic reserve -> Requested. | VKT-032, VKT-048, VKT-051 | BLOCKING | 7 | 5 | §11.3; WAL-002; KYC-001 | Must
VKT-053 | Sprint 3 | Super Admin | Wallet/Payouts | Payout queue/detail screen | Build payout review queue and detail | Review requested payouts and risk/compliance context; support approve, reject, freeze and process transitions. | Requested -> Under Review -> Approved/Rejected/Frozen -> Processing. | VKT-052, VKT-016 | BLOCKING | 6 | 5 | SA13-002..003; §11.3; §24.5 | Must
VKT-054 | Sprint 3 | Super Admin | Wallet/Payouts | Payout proof + mark paid | Implement private proof upload and Paid transition | Upload private internal payout proof, enter non-sensitive transaction reference, enforce proof-required setting when configured, then mark Paid. | Processing -> private proof -> transaction ref -> Paid. | VKT-053, VKT-014, VKT-006 | BLOCKING | 6 | 5 | SA13-004..005; BR-009..010 | Must
VKT-055 | Sprint 3 | Platform | Wallet/Payouts | Payout receipt generator | Generate agency-visible payout receipt | Generate receipt number, agency name, request ID, amount/currency, masked method, request/paid dates, Paid status, masked/non-sensitive reference and issuer details. | Mark Paid -> finalize ledger -> receipt -> agency notification. | VKT-054, VKT-012 | BLOCKING | 5 | 3 | §11.4; BR-010 | Must
VKT-056 | Sprint 3 | Agency | Wallet/Payouts | Payout history/receipt screen | Build agency payout history and receipt access | Agency can view/download generated receipts but cannot access private admin proof. | Wallet -> payouts -> Paid -> receipt; proof endpoint denied. | VKT-055, VKT-008 | BLOCKING | 4 | 3 | AG11-005; BR-009 | Must
VKT-057 | Sprint 3 | Platform | Billing/Commission | Refund/chargeback reversal service | Implement commission reversal rules | Refund during hold reverses held commission; refund after availability debits available; pending payout may be reduced/cancelled/recalculated; paid commission creates negative balance/recovery from future earnings. Never rewrite history. | Refund/chargeback -> locate original commission -> state-specific reversal -> ledger/audit/event. | VKT-048, VKT-045, VKT-046 | BLOCKING | 8 | 8 | BR-017; §28; Appendix C | Must
VKT-058 | Sprint 3 | Platform | Risk | Customer chargeback freeze/re-onboarding rules | Implement confirmed chargeback customer freeze and re-onboarding prevention | Confirmed chargeback freezes the customer, immediately disables all customer agents and production calling, blocks new resources except approved recovery payments, creates a risk event, notifies responsible parties and blocks re-onboarding where permanently banned. | Chargeback -> customer frozen -> agents disabled -> onboarding blocked -> risk/audit/notifications. | VKT-057, VKT-006, VKT-012 | BLOCKING | 8 | 8 | Risk rules §§16-24; BR-017 | Must
VKT-059 | Sprint 3 | Platform | Risk | Agency fraud/risk controls | Implement agency fraud/risk actions | Support freezing payouts/wallet, blocking customer/agent/number creation, requiring KYC/re-verification, investigation, suspension and termination while allowing existing services to be handled separately. | Risk signal -> Super Admin action -> capability/status changes -> audit/notifications. | VKT-022, VKT-058 | BLOCKING | 6 | 5 | Risk rules §§25-27 | Must
VKT-060 | Sprint 3 | Platform | Notifications | Billing/wallet notifications | Implement billing/wallet notification triggers | Implement payment success/failure, low minutes, commission available, payout requested/paid/rejected and agency restriction/suspension notification triggers. | Event -> recipient selection -> in-app/email -> preference enforcement. | VKT-012, VKT-047, VKT-055 | PARALLEL | 5 | 3 | §19; NOT-001..005 | Must
VKT-061 | Sprint 4 | Super Admin | Agents | Agent directory | Build global agent directory and diagnostics entry | List all agents by agency/customer/status/type/number; expose runtime configuration, recent calls, errors and integrations. | Agents -> filters -> detail/diagnostics. | VKT-005, VKT-016 | PARALLEL | 5 | 3 | SA5-001..003 | Must
VKT-062 | Sprint 4 | Super Admin | Agents | Lifecycle actions | Implement Super Admin agent lifecycle actions | Implement create/edit/pause/publish/clone/archive and immediate disable actions with permission checks and audit/history. | Agent action -> validation -> state transition -> audit/event. | VKT-061, VKT-008 | BLOCKING | 6 | 5 | SA5-002..004; AGT-003 | Must
VKT-063 | Sprint 4 | Agency | Agents | Agent list/create | Build agency agent directory and creation entry | List customer agents within agency scope and start creation from scratch or an allowed template. | Agency -> Agents -> Create -> source choice -> Draft. | VKT-041, VKT-061 | BLOCKING | 5 | 3 | AG3-001 | Must
VKT-064 | Sprint 4 | Agency | Agents | Agent Builder - Identity | Build Identity stage | Configure agent name, customer, use case/type, status and timezone. New agent begins Draft. | Create -> Identity -> save Draft. | VKT-063 | BLOCKING | 3 | 2 | §12.2; AGT-001 | Must
VKT-065 | Sprint 4 | Agency | Agents | Agent Builder - Voice & Language | Build Voice & Language stage | Configure provider, voice, language and supported speaking style/speed settings. | Draft -> Voice/Language -> save configuration. | VKT-064 | BLOCKING | 4 | 3 | §12.2 | Must
VKT-066 | Sprint 4 | Agency | Agents | Agent Builder - Persona & Instructions | Build Persona/Instructions stage | Configure role, goals, constraints, greeting, fallback behavior and layered instruction fields while preserving deterministic precedence. | Draft -> instructions -> resolve Platform -> Template -> Agency -> Customer -> Agent. | VKT-064, VKT-070, VKT-071 | BLOCKING | 6 | 5 | §12.2; INS-001..004 | Must
VKT-067 | Sprint 4 | Agency | Agents | Agent Builder - Knowledge | Build Knowledge attachment stage | Select allowed global/agency/customer/agent sources and attach/detach them while enforcing retrieval scope. | Builder -> Knowledge -> select sources -> attach -> resolved agent knowledge. | VKT-064, VKT-072, VKT-073 | BLOCKING | 5 | 3 | §12.2; KB-001..004; AGT-007 | Must
VKT-068 | Sprint 4 | Agency | Agents | Agent Builder - Call Handling | Build Call Handling stage | Configure inbound/outbound permissions, business hours, voicemail/fallback, silence/timeouts and interruption settings. | Builder -> Call Handling -> save -> publish preflight consumes settings. | VKT-064 | BLOCKING | 5 | 3 | §12.2 | Must
VKT-069 | Sprint 4 | Agency | Agents | Agent Builder - Tools/Actions | Build Tools/Actions stage | Select explicitly allowed normalized actions and parameter schemas; only configured tools can execute. | Builder -> Tools -> allowlist -> action schema -> runtime authorization. | VKT-064, VKT-088 | BLOCKING | 5 | 3 | §12.2; AGT-005; INT-003..004 | Must
VKT-070 | Sprint 4 | Platform | Instructions | Instruction resolution | Implement deterministic instruction inheritance/resolution | Enforce Platform Safety/Global -> Template/Base -> Agency -> Customer -> Agent precedence. Mandatory platform safety rules cannot be overridden. | Resolve at runtime/build preview -> ordered layers -> final effective instructions. | VKT-008, VKT-006 | BLOCKING | 6 | 5 | §14.1; INS-001..004 | Must
VKT-071 | Sprint 4 | Super Admin | Instructions | Global/template instruction screens | Build global and template instruction management | Manage platform safety/behavior instructions and reusable template instructions with version/audit history. | Admin -> Instructions -> edit/version -> audit -> available to agents/templates. | VKT-070, VKT-016 | PARALLEL | 4 | 3 | SA7-001..004 | Must
VKT-072 | Sprint 4 | Super Admin | Knowledge | Global knowledge screen | Build global knowledge source management | Create shared platform knowledge sources using supported source types and processing states. | Knowledge -> add source -> processing -> Ready/Failed/Stale. | VKT-014, VKT-016 | PARALLEL | 5 | 3 | SA8-001..004; KB-001..002 | Must
VKT-073 | Sprint 4 | Agency | Knowledge | Agency/customer knowledge | Build agency-wide and customer-specific knowledge management | Create reusable agency knowledge and customer-specific sources; attach/detach sources to agents; enforce source ownership. | Agency/Customer -> Knowledge -> source -> processing -> attach to agent. | VKT-072, VKT-041 | BLOCKING | 6 | 5 | AG7-001..004; KB-001..004 | Must
VKT-074 | Sprint 4 | Platform | Knowledge | Ingestion/processing | Implement knowledge processing states and failure-safe behavior | Support Queued, Processing, Ready, Failed and Stale/Needs Refresh. Failed ingestion must not break a published agent using last valid knowledge where safe. | Upload/URL/Q&A -> queue -> processing -> Ready/Failed/Stale -> safe fallback to last valid source. | VKT-014, VKT-073 | BLOCKING | 7 | 5 | KB-001..005; §28 | Must
VKT-075 | Sprint 4 | Super Admin | Templates | Template catalog screens | Build template catalog management UI | List/create/edit/version/archive reusable templates and expose metadata/visibility controls. | Templates -> list -> detail -> edit/version/archive. | VKT-005, VKT-016 | PARALLEL | 5 | 3 | SA6-001..004; TPL-001..005 | Must
VKT-076 | Sprint 4 | Super Admin | Templates | Template metadata/version/visibility | Implement template metadata, visibility and versioning | Configure industry, use case, description, languages, default voice, instructions, recommended tools/knowledge, visibility and versions; revisions cannot silently alter deployed agents. | Create template -> version -> visibility -> publish. | VKT-075, VKT-071 | BLOCKING | 6 | 5 | TPL-001..005 | Must
VKT-077 | Sprint 4 | Agency | Templates | Install/clone template | Implement independent editable template installation | Agency installs allowed template and receives an independent editable agent configuration rather than a live shared dependency. | Catalog -> Install -> visibility check -> clone configuration -> Draft agent. | VKT-076, VKT-063 | BLOCKING | 5 | 3 | TPL-002, TPL-004 | Must
VKT-078 | Sprint 4 | Platform | Telephony | Provider adapter | Implement telephony provider abstraction | Create adapter boundary for number search/purchase/assignment/release and call routing so provider-specific fields do not leak into core business logic. | Core telephony -> adapter -> provider -> normalized result. | VKT-011, VKT-010 | BLOCKING | 6 | 5 | TEL-001 | Must
VKT-079 | Sprint 4 | Agency | Phone Numbers | Number search screen | Build phone number search UI | Search available supported numbers by country/area/capability and show provider metadata needed for selection. | Phone Numbers -> search criteria -> provider -> available results. | VKT-078, VKT-008 | BLOCKING | 5 | 3 | TEL-002; AG4-001 | Must
VKT-080 | Sprint 4 | Agency | Phone Numbers | Purchase/assignment/release | Implement number purchase, assignment, release and provisioning states | Purchase only when tenant status, entitlement, payment/balance rules and provider success permit. Assign one active routing target. Release requires confirmation and impact warning. | Search -> purchase -> Pending/Active/Failed -> assign -> release -> Releasing/Released. | VKT-079, VKT-033, VKT-078 | BLOCKING | 8 | 8 | TEL-003..010; AG4-001..004 | Must
VKT-081 | Sprint 4 | Platform | Telephony | Purchase reconciliation | Implement idempotent number purchase reconciliation | Detect provider success/local timeout or local/provider ambiguity and reconcile through provider query/import or escalation without duplicate purchase. | Purchase -> timeout/partial result -> provider reconciliation -> final state. | VKT-080, VKT-012 | BLOCKING | 5 | 3 | TEL-010; §28 | Must
VKT-082 | Sprint 4 | Agency | Transfers | Destination/team screen | Build transfer destination/team management | Create verified/validated transfer destinations such as phone number, department, queue or supported SIP/client target. | Transfers -> destination -> validation/verification -> active target. | VKT-078, VKT-008 | BLOCKING | 5 | 3 | XFER-001..002; AG6-001 | Must
VKT-083 | Sprint 4 | Agency | Transfers | Rules screen | Build transfer rules | Configure triggers, business hours, timeout/no-answer and fallback behavior, including conditional rules. | Destination -> trigger -> business hours -> transfer -> fallback. | VKT-082, VKT-064 | BLOCKING | 5 | 3 | XFER-003..005; AG6-002 | Must
VKT-084 | Sprint 4 | Agency | Agents | Agent Builder - Integrations | Build integration/action mapping stage | Map normalized agent actions to authorized CRM/automation/API connections; credentials remain hidden. | Builder -> Integration -> connection/action -> test -> save mapping. | VKT-069, VKT-086 | BLOCKING | 5 | 3 | §12.2; INT-001..008 | Must
VKT-085 | Sprint 4 | Agency | Agents | Agent Builder - Transfers/Number/Compliance | Build Transfers, Phone Number and Compliance stages | Configure transfers, assigned phone number and compliance fields including recording disclosure, prohibited behavior and required disclaimers where configured. | Builder -> Transfers -> Number -> Compliance -> preflight-ready configuration. | VKT-080, VKT-083, VKT-084 | BLOCKING | 6 | 5 | §12.2; TEL-005..006; XFER-003..005 | Must
VKT-086 | Sprint 4 | Platform | Integrations | Connection service | Implement integration ownership/OAuth/credential isolation | Support agency/customer-owned connections, OAuth where supported, encrypted refresh tokens, revocation and dependent-action disablement. | Connect -> OAuth/credential storage -> Active -> disconnect -> revoke/disable dependent actions. | VKT-010, VKT-008 | BLOCKING | 7 | 5 | INT-001..002, INT-008 | Must
VKT-087 | Sprint 4 | Agency | Integrations | Connection screens | Build integrations UI | Connect authorized HubSpot, Salesforce, Zoho, QuickBooks and configure n8n/Zapier/Make through webhook/API patterns; never display stored credentials/tokens. | Integrations -> provider -> connect -> status -> test -> active/error. | VKT-086, VKT-041 | BLOCKING | 6 | 5 | AG8-001..005 | Must
VKT-088 | Sprint 4 | Platform | Integrations | Normalized action runtime | Implement normalized action execution | Implement action schemas, timeout/error behavior, sanitized failures, provider rate limits and authorization so only configured actions execute. | Agent -> normalized action -> connection -> provider/API -> sanitized result/error. | VKT-086, VKT-087, VKT-069 | BLOCKING | 8 | 8 | INT-003..007 | Must
VKT-089 | Sprint 4 | Agency | Webhooks | Endpoint CRUD/subscription screens | Build webhook endpoint management | Create/update/disable endpoints, subscribe to allowed events, generate/rotate tenant-specific signing secret and send safe test events. | Webhooks -> endpoint -> event subscriptions -> secret -> test -> active. | VKT-010, VKT-012, VKT-041 | BLOCKING | 6 | 5 | AG9-001..005; WH-001..005 | Must
VKT-090 | Sprint 4 | Platform | Webhooks | Signed delivery/retry/replay | Implement signed webhook delivery | Create unique delivery/event IDs, sign payloads, retry transient failures with bounded backoff, log status/attempts/timestamps, allow eligible replay and support synchronous agent/knowledge webhook patterns. | Domain event -> scoped endpoint -> signed delivery -> response -> retry/replay. | VKT-089, VKT-012, VKT-011 | BLOCKING | 8 | 8 | WH-001..008; §30.3 | Must
VKT-091 | Sprint 5 | Agency | Agents | Agent Builder - Test | Build browser/simulator test screen | Allow agent test/simulator execution with transcript and tool traces where enabled; Draft/Testing agents cannot receive production traffic. | Builder -> Test -> simulator -> transcript/tool trace -> return to builder. | VKT-064, VKT-067, VKT-068, VKT-069, VKT-084, VKT-085 | BLOCKING | 7 | 5 | AG3-003; §12.2 | Must
VKT-092 | Sprint 5 | Platform | Agents | Publish preflight | Implement agent publish validation | Before publish validate customer status, plan entitlement, number/routing, instructions, voice/provider and required compliance fields. | Draft/Testing -> preflight -> pass -> Active; fail -> actionable validation errors and no production traffic. | VKT-091, VKT-033, VKT-036, VKT-080, VKT-070 | BLOCKING | 7 | 5 | AGT-002 | Must
VKT-093 | Sprint 5 | Agency | Agents | Publish/lifecycle screen | Build publish, activate, pause and clone actions | Implement publish/activate/deactivate/pause and clone flows subject to status, entitlement and permissions. Published changes preserve audit/revision history. | Test -> Publish -> Active; Active -> Paused; configuration retained. | VKT-092, VKT-062 | BLOCKING | 5 | 3 | AG3-004..005; AGT-003..004 | Must
VKT-094 | Sprint 5 | Platform | Calls | Call lifecycle | Implement call ingestion and lifecycle persistence | Record Vokit/provider IDs, tenant ownership, direction, caller/callee, timestamps, status/disconnect reason, duration and billable usage fields. | Call started -> answered -> terminal state -> persisted Call. | VKT-078, VKT-093, VKT-005 | BLOCKING | 8 | 8 | CALL-001..002; §16.1 | Must
VKT-095 | Sprint 5 | Platform | Calls | Inbound routing | Implement inbound routing to assigned agent/fallback | Route incoming calls to the assigned active agent and configured fallback; enforce agent/customer/agency state and provider policy. | Inbound number -> assignment -> active agent -> call; otherwise configured fallback. | VKT-080, VKT-093, VKT-094 | BLOCKING | 8 | 8 | TEL-004..006 | Must
VKT-096 | Sprint 5 | Platform | Calls | Outbound calling | Implement outbound calling/caller ID where enabled | Support outbound agent calling where enabled by configuration/provider policy, using authorized caller ID and normalized number rules. | Agent outbound -> entitlement/config check -> authorized caller ID -> provider -> Call. | VKT-095, VKT-093 | BLOCKING | 6 | 5 | TEL-006; §2.1 | Must
VKT-097 | Sprint 5 | Platform | Calls | Usage charging | Implement billable usage and entitlement linkage | Calculate billable usage consistently and link usage to customer subscription/balance, plan allocation and overage/hard-stop behavior. | Call duration -> billable units -> plan allocation/overage -> usage/balance. | VKT-094, VKT-043 | BLOCKING | 8 | 8 | CALL-002; PLAN-002..005 | Must
VKT-098 | Sprint 5 | Platform | Calls | Artifacts | Implement recording/transcript/summary artifact service | Persist recording/transcript/summary references and optional sentiment/outcome/tool activity; enforce role, tenant, legal configuration and retention metadata. | Call completed -> artifacts ready -> permission check -> authorized viewer. | VKT-094, VKT-014 | BLOCKING | 8 | 8 | CALL-003..005; PRIV-003..004 | Must
VKT-099 | Sprint 5 | Platform | Transfers | Human handoff runtime | Implement transfer execution and call linkage | Execute configured transfer triggers/business hours/fallback; preserve context/whisper where supported and record transfer attempt/outcome in call record. | Call -> trigger -> destination -> connect/no-answer -> fallback -> call outcome. | VKT-083, VKT-095, VKT-094 | BLOCKING | 7 | 5 | XFER-003..007 | Must
VKT-100 | Sprint 5 | Super Admin | Calls | Global call list/detail | Build Super Admin call monitoring | Search all calls by agency/customer/agent/number/date/status/direction; detail shows provider ID, timestamps, duration, billable units, artifacts and tool activity; platform cost is permission-gated. | Calls -> filters -> detail -> permission-gated artifacts/cost. | VKT-094, VKT-098, VKT-016 | PARALLEL | 6 | 5 | SA14-001..004 | Must
VKT-101 | Sprint 5 | Agency | Calls | Agency call list/detail | Build agency call monitoring | Agency-wide call list/detail with filters and recording/transcript/summary/outcome/tools where enabled, subject to customer agreement/platform privacy policy. | Agency -> Calls -> filter -> detail -> privacy authorization. | VKT-100, VKT-008 | BLOCKING | 5 | 3 | AG5-001..003 | Must
VKT-102 | Sprint 5 | Customer | Portal Shell | Layout/navigation | Build Customer Portal shell | Create authenticated customer layout, responsive monitoring/basic-action navigation and customer-scope route guards. | Customer login -> shell -> customer-owned modules only. | VKT-042, VKT-008 | BLOCKING | 5 | 3 | §9; NFR-009 | Must
VKT-103 | Sprint 5 | Customer | Dashboard | Dashboard | Build Customer dashboard | Show agents, calls this month, minutes used/remaining, plan, invoice status, recent calls and service alerts for low minutes/payment due/agent offline/important notifications. | Login -> dashboard -> KPI/alert -> linked module. | VKT-097, VKT-043, VKT-102 | BLOCKING | 6 | 5 | CU1-001..002 | Must
VKT-104 | Sprint 5 | Customer | Agents | Agent list/detail | Build customer agent monitoring | Show assigned agents, status, number and high-level configuration. Editing is disabled by default; only explicitly permitted actions/fields are available. | Customer -> Agents -> detail -> permission check -> optional pause/resume. | VKT-093, VKT-102 | BLOCKING | 5 | 3 | CU2-001..003 | Must
VKT-105 | Sprint 5 | Customer | Calls | Call history/detail | Build customer call history and artifacts | Show only customer-owned calls; filter by agent/number/date/direction/outcome; display recording/transcript/summary only if enabled/authorized; export only when permitted. | Customer -> Calls -> filters -> detail -> artifact authorization. | VKT-101, VKT-098, VKT-102 | BLOCKING | 6 | 5 | CU3-001..004 | Must
VKT-106 | Sprint 5 | Customer | Usage | Usage/minutes | Build customer usage and top-up screen | Show included, consumed, remaining and additional minutes; breakdown by agent/date where feasible; allow purchase of Vokit-offered additional minute packages. | Customer -> Usage -> balances/breakdown -> Top-up -> payment -> additional minutes. | VKT-097, VKT-044, VKT-102 | BLOCKING | 6 | 5 | CU4-001..003 | Must
VKT-107 | Sprint 5 | Customer | Billing | Invoices/payments | Build customer invoices and payment UI | List open/paid/failed/refunded invoices; pay outstanding invoices through Vokit; add/update payment method through processor-hosted secure flow where possible; download receipts/invoices. | Customer -> Billing -> invoice -> pay -> processor -> Paid/Failed -> receipt. | VKT-043, VKT-044, VKT-102 | BLOCKING | 7 | 5 | CU5-001..004; SEC-004 | Must
VKT-108 | Sprint 5 | Customer | Knowledge | Knowledge | Build customer knowledge view/edit where granted | View customer knowledge attached to agents; upload/edit only where agency explicitly grants permission. | Customer -> Knowledge -> source -> permission -> view/edit -> processing. | VKT-073, VKT-074, VKT-102 | PARALLEL | 4 | 3 | CU6-001..002 | Must
VKT-109 | Sprint 5 | Customer | Integrations | Integration status/self-service | Build customer integration visibility and permitted self-service | Show integrations relevant to customer; allow customer-owned connection only when agency enables self-service. | Customer -> Integrations -> status -> if enabled connect customer-owned account. | VKT-087, VKT-102 | PARALLEL | 4 | 3 | CU7-001..002 | Must
VKT-110 | Sprint 5 | Customer | Team/Settings | Team/settings | Build customer team, notifications and profile settings | Invite/manage customer team by role; configure notification preferences; manage allowed business/contact settings. | Customer -> Team/Settings -> permission -> update/invite. | VKT-102, VKT-008 | PARALLEL | 5 | 3 | CU8-001..003 | Must
VKT-111 | Sprint 5 | Agency | Team/Settings | Team/settings | Build agency team, notification and security settings | Invite/assign/revoke agency users within allowed roles; configure notification preferences, allowed profile/branding fields and sessions/password/MFA when supported. | Agency -> Team/Settings -> invite/role/revoke; Preferences/Security updates. | VKT-008, VKT-034 | PARALLEL | 6 | 5 | AG13-001..003; AG14-001..003 | Must
VKT-112 | Sprint 5 | Super Admin | Users/Roles | Platform users/roles | Build Super Admin user and role management | Invite/disable platform users; create role/permission bundles; keep KYC, payout, wallet adjustment, commission edit and impersonation permissions explicit. | Admin -> Users/Roles -> role bundle -> assign -> access enforced server-side. | VKT-008, VKT-016 | BLOCKING | 6 | 5 | SA18-001..003 | Must
VKT-113 | Sprint 5 | Platform | Notifications | Notification engine/preferences | Complete notification preference and template engine | Support in-app/email, validated template variables, escaped untrusted content, mandatory notice categories and delivery status where provider supports. | Event -> preference check -> mandatory/non-mandatory -> render -> deliver -> log. | VKT-034, VKT-060, VKT-006 | BLOCKING | 7 | 5 | NOT-001..005 | Must
VKT-114 | Sprint 5 | Super Admin | Notifications | Template/delivery/announcement screens | Build Super Admin notification administration | Manage system email/in-app templates, inspect delivery status where supported and send platform/agency-targeted announcements. | Admin -> Notifications -> template/delivery/announcement -> scoped recipients. | VKT-113, VKT-016 | PARALLEL | 5 | 3 | SA16-001..003 | Must
VKT-115 | Sprint 6 | Super Admin | Integrations | Provider registry/connection visibility | Build provider registry and tenant connection visibility | Configure available integration/provider strategy and inspect tenant connection status without exposing secrets; allow disabling compromised connections. | Admin -> Providers/Connections -> status -> disable if compromised. | VKT-086, VKT-016 | PARALLEL | 5 | 3 | SA15-001..004 | Must
VKT-116 | Sprint 6 | Super Admin | Webhooks | Webhook logs/replay | Build webhook delivery log and replay UI | Inspect endpoint, event, status, retries, timestamps and response codes/metadata; replay only eligible failed deliveries. | Admin -> Webhooks -> delivery detail -> replay authorization -> signed resend. | VKT-090, VKT-016 | PARALLEL | 5 | 3 | SA15-003; WH-005..006 | Must
VKT-117 | Sprint 6 | Super Admin | Transfers | Transfer directory/diagnostics | Build transfer monitoring | View tenant transfer destinations/rules; disable unsafe/invalid targets and inspect failed transfers where supported. | Admin -> Transfers -> target/rule -> disable/diagnose -> audit. | VKT-083, VKT-099 | PARALLEL | 4 | 3 | SA10-001..003 | Must
VKT-118 | Sprint 6 | Super Admin | Audit | Audit log search/detail | Build immutable audit log search/detail | Search by actor, action, entity, tenant, IP/time and severity. Do not allow edit/delete. Redact secrets/full payment data/raw KYC content. | Action -> AuditEvent -> searchable immutable record. | VKT-006, VKT-016 | BLOCKING | 5 | 3 | SA17-001..003; AUD-001..005 | Must
VKT-119 | Sprint 6 | Super Admin | Overrides | High-risk override framework | Implement Super Admin override workflow | Allow authorized overrides for agency/customer status, feature gates, agent status, number assignment, plan, KYC, payout eligibility/state, wallet freeze and commission rate. Require reason and production-call impact warning where applicable. | Select override -> permission -> impact warning -> reason/confirmation -> state/ledger -> audit. | VKT-008, VKT-022, VKT-039, VKT-054, VKT-062, VKT-118 | BLOCKING | 7 | 5 | §21.1; BR-008; AUD-004..005 | Must
VKT-120 | Sprint 6 | Super Admin | Settings | Platform settings | Build platform settings UI | Configure commercial, payout, telephony, AI, compliance, notifications, security and feature-flag settings listed by the SRS. | Settings -> category -> validate -> save -> centralized config. | VKT-010, VKT-016 | BLOCKING | 7 | 5 | §22 | Must
VKT-121 | Sprint 6 | Platform | Settings | Business policy/config service | Implement centralized configurable business rules | Centralize hold duration, payout thresholds, commissionability, KYC gates, recording disclosure/retention, allowed countries/providers and other policy controls instead of duplicating them in UI code. | Module -> policy service -> current configured rule -> decision. | VKT-120, VKT-033, VKT-047, VKT-046 | BLOCKING | 6 | 5 | NFR-014 | Must
VKT-122 | Sprint 6 | Platform | Privacy | Retention/deletion workflow | Implement configurable retention and deletion-request controls | Support retention for recordings, transcripts, logs, KYC and financial records subject to legal constraints; support customer/agency deletion requests with financial/KYC/legal exceptions. | Policy -> retention metadata -> scheduled action -> deletion request -> exceptions -> audit. | VKT-098, VKT-014, VKT-121, VKT-118 | BLOCKING | 7 | 5 | PRIV-001..006 | Must
VKT-123 | Sprint 6 | Platform | Privacy | Authorized data export | Implement authorized tenant data export | Provide authorized operational data export where supported; enforce tenant scope and audit sensitive exports. | Tenant request -> authorization -> scoped export -> audit. | VKT-008, VKT-118 | PARALLEL | 4 | 3 | PRIV-007; CALL-007 | Must
VKT-124 | Sprint 6 | Super Admin | Reporting | Platform reports | Build platform operational/financial reporting | Report MRR, agencies, customers, agents, calls, minutes, failed payments, commission liability, held/available wallet, pending payouts, payout aging, KYC aging, provider costs and gross margin using authoritative data. | Reports -> period/timezone/tenant filters -> ledger/payment/call sources -> export where permitted. | VKT-048, VKT-094, VKT-032, VKT-043 | BLOCKING | 7 | 5 | §29; RPT-001..005 | Must
VKT-125 | Sprint 6 | Agency | Reporting | Agency dashboard data | Complete agency KPI/report data layer | Provide customer MRR, expected commission MRR, earned/held/available/lifetime paid, customers, agents, calls, minutes, top customers and payout status for agency dashboard. | Agency dashboard -> scoped reporting query -> KPI/trend/alerts. | VKT-124, VKT-051 | PARALLEL | 5 | 3 | AG1-001..003; §29 | Must
VKT-126 | Sprint 6 | Customer | Reporting | Customer dashboard data | Complete customer KPI/report data layer | Provide plan, minutes used/remaining, call count/duration, agent activity, invoice/payment status and top-up history for customer views. | Customer dashboard -> customer-scoped reporting query -> cards/lists. | VKT-124, VKT-103 | PARALLEL | 4 | 3 | CU1-001; §29 | Must
VKT-127 | Sprint 6 | Platform | Observability | Critical workflow telemetry | Implement structured logs, metrics, traces and correlation IDs | Add observability for authentication, payments, commission/ledger, payout, KYC, telephony, webhooks, integrations and calls. Redact secrets and sensitive documents. | Request/event -> correlation ID -> structured telemetry -> alerting. | VKT-011, VKT-012, VKT-010 | BLOCKING | 6 | 5 | NFR-006; SEC-015 | Must
VKT-128 | Sprint 6 | Platform | Reliability | Backup/recovery validation | Implement automated backups and recovery test | Configure automated database/configuration backup and execute a recovery validation sufficient for production release. | Scheduled backup -> stored backup -> restore test -> documented result. | VKT-015, VKT-127 | BLOCKING | 5 | 3 | NFR-007 | Must
VKT-129 | Sprint 6 | QA | Automated Tests | Financial state tests | Automate commission/wallet/payout state transition tests | Cover payment success, independent 15-day holds, reversal during/after hold, payout reservation race, payout states, negative balance and corrective ledger behavior. | Arrange financial state -> event -> assert ledger/state/balance invariants. | VKT-047, VKT-048, VKT-052, VKT-057 | BLOCKING | 8 | 8 | §31.2; WAL-001..007 | Must
VKT-130 | Sprint 6 | QA | Automated Tests | Tenant isolation tests | Automate cross-tenant authorization tests | Verify agency cannot access another agency's customers/calls/agents/knowledge/wallet/payouts and customer cannot access other customer data; API manipulation cannot bypass restrictions. | Actor A -> request tenant B ID -> deny/not-found without disclosure. | VKT-008, VKT-033, VKT-094 | BLOCKING | 7 | 8 | §31.2; TEN-001..005 | Must
VKT-131 | Sprint 6 | QA | Automated Tests | Idempotency tests | Automate payment/webhook/payout/number idempotency tests | Verify duplicate payment webhooks, duplicate payout requests/reservation races and irreversible number purchases do not double-apply. | Duplicate event/request -> same outcome -> no duplicate side effect. | VKT-045, VKT-052, VKT-081, VKT-090 | BLOCKING | 7 | 8 | §31.2; NFR-005 | Must
VKT-132 | Sprint 6 | QA | Security | Security test suite | Run security checks for auth/RBAC/secrets/webhooks/uploads/payments | Validate secure sessions, CSRF, rate limits, secret isolation, inbound/outbound webhook signatures, upload controls, payment tokenization and log redaction. | Security test -> exploit attempt -> deny/secure result -> evidence. | VKT-009, VKT-010, VKT-014, VKT-090, VKT-118 | BLOCKING | 8 | 8 | §25; §31.2 | Must
VKT-133 | Sprint 7 | Super Admin | UI Completion | Dashboard drilldowns/date filters | Complete dashboard filter and drilldown behavior | Verify every dashboard card routes to the correct filtered module view and date filters support today, 7 days, 30 days, month-to-date and custom range. | Dashboard -> filter -> KPI -> drilldown -> expected filtered list. | VKT-017, VKT-124 | BLOCKING | 3 | 2 | SA1-004..005 | Must
VKT-134 | Sprint 7 | Super Admin | UI Completion | All portal screens | Complete Super Admin screens and permission-aware states | Finalize Agencies, Customers, KYC, Agents, Templates, Instructions, Knowledge, Phone Numbers, Transfers, Plans, Billing, Wallet/Payouts, Calls, Integrations/Webhooks, Notifications, Audit, Users/Roles and Settings with loading, empty, error and permission states. | Module -> list -> detail/form -> action -> confirmation -> result/error -> audit/event where required. | VKT-018, VKT-020, VKT-030, VKT-032, VKT-061, VKT-075, VKT-071, VKT-072, VKT-080, VKT-117, VKT-036, VKT-049, VKT-053, VKT-100, VKT-115, VKT-116, VKT-114, VKT-118, VKT-112, VKT-120 | BLOCKING | 8 | 5 | §7.1..7.19 | Must
VKT-135 | Sprint 7 | Agency | UI Completion | All portal screens | Complete Agency portal screens and state/permission UX | Finalize Dashboard, Customers, Agents/Builder, Phone Numbers, Calls, Transfers, Knowledge, Integrations, Webhooks, Plans/Billing visibility, Wallet/Payouts, KYC, Team and Notifications/Settings including loading/empty/error/disabled states and status/capability messaging. | Agency module -> scoped API -> permission/status gate -> screen -> action -> feedback. | VKT-040, VKT-063, VKT-091, VKT-093, VKT-079, VKT-101, VKT-082, VKT-073, VKT-087, VKT-089, VKT-051, VKT-052, VKT-056, VKT-029, VKT-111, VKT-125 | BLOCKING | 8 | 5 | §8.1..8.14 | Must
VKT-136 | Sprint 7 | Customer | UI Completion | All portal screens | Complete Customer portal screens and customer-scope UX | Finalize Dashboard, Agents, Calls, Usage/Minutes, Invoices/Payments, Knowledge, Integrations and Team/Settings with responsive behavior and customer-only data visibility. | Customer module -> customer-scoped API -> permission -> screen/action -> feedback. | VKT-103, VKT-104, VKT-105, VKT-106, VKT-107, VKT-108, VKT-109, VKT-110, VKT-126 | BLOCKING | 8 | 5 | §9.1..9.8; TEN-005 | Must
VKT-137 | Sprint 7 | Platform | Edge Cases | Payment/billing edge cases | Verify payment and commission edge cases | Test repeated payment webhook, payment success with commission-write failure, refund during hold, refund after availability, chargeback after payout, commission-rate changes and payment-failure service rules. | Payment -> event/edge case -> idempotent/reconciled ledger outcome -> notifications/audit. | VKT-129, VKT-131, VKT-057 | BLOCKING | 6 | 5 | §28; Appendix C | Must
VKT-138 | Sprint 7 | Platform | Edge Cases | Payout/risk edge cases | Verify payout and risk edge cases | Test agency suspension with requested payout, KYC expiry with available funds, accidental Paid state, missing proof, payout race conditions and negative balance recovery. | Risk/payout event -> policy gate -> state/ledger correction -> audit/notification. | VKT-129, VKT-119, VKT-054 | BLOCKING | 6 | 5 | §28; §24.5 | Must
VKT-139 | Sprint 7 | Platform | Edge Cases | Telephony/agent edge cases | Verify number/call/agent failure behavior | Test provider/local number purchase mismatch, customer out of minutes during call, integration timeout during call, knowledge ingestion failure, agent pause/error/fallback and active-call override warnings. | Runtime failure -> configured fallback/reconciliation -> safe continuation/disablement -> audit. | VKT-081, VKT-097, VKT-088, VKT-074, VKT-119 | BLOCKING | 7 | 5 | §28; AGT-008; TEL-010 | Must
VKT-140 | Sprint 7 | Platform | Risk | Chargeback shutdown and ban | Run confirmed chargeback shutdown and re-onboarding prevention | Verify chargeback freezes customer, immediately disables all customer agents and production calling, blocks new minutes/numbers/agents/subscriptions/payment except approved recovery, notifies agency/Super Admin, reverses commission by state, and blocks re-onboarding across agencies where permanently banned. | Chargeback -> customer freeze -> agent shutdown -> restrictions -> commission reversal -> risk/audit/notifications -> re-onboarding block. | VKT-058, VKT-059, VKT-137, VKT-139 | BLOCKING | 7 | 8 | Risk rules §§16-24; core rules summary | Must
VKT-141 | Sprint 7 | QA | E2E | Agency onboarding/KYC | Run complete agency lifecycle acceptance test | Create agency as Super Admin, send invitation, accept/create credentials, complete KYC, review/decision, verify activation and ensure payout remains blocked until KYC Verified. | SA create -> invitation -> Agency onboarding/KYC -> review -> Verified -> Active. | VKT-019, VKT-024, VKT-029, VKT-032, VKT-033 | BLOCKING | 5 | 5 | §6.1; §31.1 | Must
VKT-142 | Sprint 7 | QA | E2E | Customer/payment/commission | Run customer commercial flow acceptance test | Create customer when agency is permitted, assign versioned plan, create invoice, pay Vokit directly, create exactly one commission with correct rate snapshot and 15-day availability date, activate entitlements and notifications. | Agency -> Customer -> Plan -> Invoice -> Payment -> Commission On Hold -> entitlements. | VKT-040, VKT-043, VKT-044, VKT-046, VKT-047, VKT-060 | BLOCKING | 6 | 8 | §10.3; §31.1 | Must
VKT-143 | Sprint 7 | QA | E2E | Number/agent/call | Run telephony production-path acceptance test | Purchase/assign number, configure inbound routing, publish compliant agent, place inbound call, verify correct tenant/customer agent receives it and Call record/artifacts/usage are written according to configuration. | Number -> Agent -> Publish -> Inbound call -> Call record -> usage/artifacts. | VKT-080, VKT-093, VKT-095, VKT-097, VKT-098 | BLOCKING | 6 | 8 | §15; §16; §31.1 | Must
VKT-144 | Sprint 7 | QA | E2E | Agent integration/transfer | Run tools, integration and human handoff acceptance test | Configure authorized integration/action and transfer destination/rules, test action execution with sanitized failures and verify transfer attempt/outcome is captured. | Agent -> action/transfer -> provider/integration -> result/fallback -> call/audit. | VKT-088, VKT-090, VKT-099 | BLOCKING | 5 | 5 | §17; §18; §31.1 | Must
VKT-145 | Sprint 7 | QA | E2E | Customer portal isolation | Verify customer portal scope and permitted functions | Confirm customer sees only owned agents/calls/invoices/usage, can pay invoices/top up where configured, and cannot access agency/platform data or restricted agent fields. | Customer login -> scoped data -> permitted action -> cross-tenant attempt denied. | VKT-136, VKT-130, VKT-107 | BLOCKING | 5 | 5 | §9; TEN-005; §31.1 | Must
VKT-146 | Sprint 7 | QA | E2E | Payout lifecycle | Run payout request-to-receipt acceptance test | Verify only Available funds can be requested, atomic reservation occurs, admin review/actions work, private proof remains inaccessible to agency, Paid generates receipt and notification. | Available -> Withdraw -> Requested -> Review -> Approved -> Processing -> proof -> Paid -> receipt. | VKT-052, VKT-053, VKT-054, VKT-055, VKT-056 | BLOCKING | 5 | 8 | §11.3; §11.4; §31.1 | Must
VKT-147 | Sprint 7 | QA | Release | Must-requirement regression | Execute requirement-by-requirement Must regression | Run traceable regression covering all Must requirements in the SRS, with failures linked to exact requirement IDs and no scope additions. | Requirement -> test -> pass/fail -> defect -> retest. | VKT-129, VKT-130, VKT-131, VKT-132, VKT-141, VKT-142, VKT-143, VKT-144, VKT-145, VKT-146 | BLOCKING | 8 | 8 | All Must requirements | Must
VKT-148 | Sprint 7 | QA | Release | Release gate verification | Verify SRS functional and engineering/QA release gates | Verify agency/KYC/customer/payment/commission/wallet/payout, suspension, telephony, customer scope, signed integrations/webhooks, reversal, roles, automated tests and security review gates. | Release checklist -> evidence -> gate pass/fail -> sign-off. | VKT-147 | BLOCKING | 5 | 5 | §31.1; §31.2 | Must
VKT-149 | Sprint 7 | Operations | Release | Production configuration/runbook | Prepare production configuration and operational runbook | Configure providers, currencies, business-day/payout settings, compliance/retention settings, feature flags, notification sender and operational runbook without hard-coded secrets. Document unresolved jurisdiction/legal dependencies. | Staging config -> reviewed production config -> secrets -> smoke test -> runbook. | VKT-120, VKT-121, VKT-127, VKT-128, VKT-148 | BLOCKING | 6 | 5 | §22; §26; NFR-006..007 | Must
VKT-150 | Sprint 7 | Operations | Release | Production deployment/smoke/rollback | Deploy V1 and validate critical production paths | Deploy the release, run smoke tests for authentication, tenancy, agency/KYC gate, customer creation, payment/commission, payout controls, number/agent/call routing and customer isolation. Confirm rollback readiness. | Deploy -> smoke -> monitor -> accept or rollback. | VKT-149 | BLOCKING | 6 | 5 | §31; NFR-001..007 | Must
VKT-151 | Sprint 7 | Product/QA | Release | Final baseline sign-off/deferred scope | Close release with explicit V1 boundary | Record Product, Engineering, QA, Finance/Operations and Compliance/Legal sign-off. Confirm explicitly deferred capabilities remain outside V1. | Release gates pass -> sign-off -> production baseline; deferred items remain outside V1. | VKT-150 | BLOCKING | 3 | 2 | §2.2; §32; SRS Baseline Sign-off | Must

## Sprint Summary
Sprint / Day | Tasks | Hours | Points
Sprint 1 | 15 | 90 | 69
Sprint 2 | 19 | 97 | 70
Sprint 3 | 26 | 158 | 127
Sprint 4 | 30 | 168 | 126
Sprint 5 | 24 | 147 | 116
Sprint 6 | 18 | 107 | 86
Sprint 7 | 19 | 113 | 104

## Portal Summary
Portal / Layer | Tasks | Hours | Points
Platform | 52 | 337 | 278
Super Admin | 38 | 208 | 150
Agency | 34 | 181 | 128
QA | 12 | 75 | 84
Customer | 12 | 64 | 46
Operations | 2 | 12 | 10
Product/QA | 1 | 3 | 2

## Dependency Summary
Dependency Category | Tasks | Hours | Points
BLOCKING | 124 | 751 | 610
PARALLEL | 27 | 129 | 88